## 📌 COVER
KAYAN INNOVATION, ENTREPRENEURSHIP & WORK ENVIRONMENTS LLC
شركة كيان للابتكار وريادة الأعمال وبيئات العمل ذ.م.م
TECHNOLOGY MASTER OPERATING SYSTEM
KAY-TECH-MASTER-OS-001 v1.0 ¦ FINAL DRAFT ¦ 16 April 2026
Platform · Website · App Modules · Ready Products · 48-Month RWP · Dev Accountability · ICT Governance
Document Code | KAY-TECH-MASTER-OS-001 v1.0
Date Issued | 16 April 2026
Status | FINAL DRAFT — CEO Approved. Share with Dev Team.
Classification | CONFIDENTIAL — Dev Team + CEO + Finance
Prepared By | CEO Office — Maher Farea (m.farea@kayanwork.com)
Supersedes | KAY-TECH-OS-008 v1.0–v6.0 + all ICT planning docs
Scope | Full Kayan Technology OS: platform, website, apps, ICT, RWP
Go-Live | 01 May 2026 (Phase 1 non-negotiable)
Key Constraint | OPEX Tech Ceiling: $1,200/month. Total OPEX ceiling: $4,510/month
OPEX Note | Developer cost NOT included in tech $1,200 sub-ceiling — budgeted in Staffing
WORKBOOK NAVIGATOR — 15 SHEETS
📌 COVER |  | Document control, inventory, navigator
📊 DASHBOARD |  | Executive KPIs, platform status, budget snapshot
🗺️ 48M RWP |  | Full 48-month rolling work plan, month-by-month, all categories
🌐 PLATFORMS |  | All 8 platforms, 11 web app modules, domain map
🛍️ READY PRODUCTS |  | Fixed-scope product catalog for client commissions
👥 DEV TEAM |  | Dev 1, Dev 2, intern accountability, sprint tracker, rules
📋 WEBSITE SPECS |  | Page-by-page kayanwork.com specifications (all 8 pages)
📱 APP MODULES |  | 11 mandatory web app module specs (from KAY-TECH-OS-008 v5)
💰 BUDGET & ROI |  | Full ICT + platform budget, CAPEX, OPEX, ROI analysis
🔧 TOOLS REGISTER |  | All 22 subscriptions, AI tools, SaaS licenses
✅ E-APPROVALS |  | 20 digital approval workflows — all on Power Automate (free)
🔒 SECURITY |  | ICT security controls, compliance checklist
📑 DOCS INDEX |  | All 25 ICT policy documents — status and owners
👤 USER MGMT |  | RBAC matrix, user register, onboarding SOP
📧 MUSTAFA BRIEF |  | Clean standalone brief for Dev Lead — what to build and by when
kayanwork.com ¦ m.farea@kayanwork.com ¦ +967 2 236655 ¦ Aden, Yemen ¦ © 2026 Kayan Innovation LLC

## 📊 DASHBOARD
📊 EXECUTIVE DASHBOARD — KAYAN TECHNOLOGY OS ¦ 16 April 2026
PLATFORM & LAUNCH KPIs
KPI | Target | Status | Owner | Due | Risk
Platform uptime | ≥ 99.5%/month | PLANNED | Dev 1 | Day-1 | Revenue halt if below
kayanwork.com Lighthouse | ≥ 80 all pages | IN PROGRESS | Dev 2 | 28 Apr 2026 | Go-live blocked if < 80
Staff 2FA activated | 100% all staff | PENDING | Dev Lead | M365 activation | Security gap
All 11 modules functional | 11/11 staging pass | IN PROGRESS | Dev 1+2 | 22 Apr 2026 | Go-live blocked
Escrow gate enforcement | 100% — zero exceptions | PLANNED | Dev 1 | Day-1 | Company-level risk
Client reg → first SOW | ≤ 7 days | PLANNED | CEO + Ops | Day-1 | Revenue delayed
YETO API keys registered | 8/8 free keys active | CRITICAL | CEO | 23 Apr 2026 | 5,000+ data points blocked
ICT policies issued | 25/25 by Jun 2026 | DRAFT | Dev Lead | Jun 2026 | Compliance gap
Website visit → register | ≥ 3% conversion | PLANNED | CEO + Mktg | Day-1 | High CAC
Freelancer → T2 verified | ≤ 14 days | PLANNED | Ops Admin | Day-1 | Delivery gap
Audit trail completeness | 100% | PLANNED | Dev 1 | Day-1 | AML/regulatory risk
Mobile Lighthouse (3G) | ≥ 80 | IN PROGRESS | Dev 2 | 28 Apr 2026 | Talent adoption fails
PLATFORM STATUS
Platform | URL | Phase | Go-Live | Status | Dev Owner
Corporate Website (14p bilingual) | kayanwork.com | 1 — Day-1 | 01 May 2026 | IN PROGRESS | Dev 2
Managed Delivery + Escrow | platform.kayanwork.com | 1 — Day-1 | 01 May 2026 | IN PROGRESS | Dev 1
Hub Booking System | space.kayanwork.com | 1 — Day-1 | 15 May 2026 | PLANNED | Dev 1+2
Volunteers Portal | volunteers.kayanwork.com | 1 — Day-1 | 01 May 2026 | PLANNED | Dev 2
Impact Dashboard | impact.kayanwork.com | 1 — Month 3 | 01 Aug 2026 | PLANNED | Dev 2
Admin Panel (RBAC) | admin.kayanwork.com | 1 — Day-1 | 01 May 2026 | IN PROGRESS | Dev 1
Staff Portal (Phase 1=SP) | staff.kayanwork.com | 1/Phase2 | 30 Apr 2026 | NOT STARTED | CEO+Dev1
Academy LMS | academy.kayanwork.com | 2 — Jul 2026 | 01 Jul 2026 | PLANNED | Dev 1+2
Yeto Talent Marketplace | yeto.kayanwork.com | 2 — Aug 2026 | 01 Aug 2026 | PLANNED | Dev 1+2
Bidding Module | platform.kayanwork.com/bid | 2 — Aug 2026 | 01 Aug 2026 | PLANNED | Dev 1
API Gateway | api.kayanwork.com | Phase 2 — M6+ | Oct 2026 | PLANNED | Dev 1
BUDGET SNAPSHOT (USD) — TECH OPEX CEILING: $1,200/MONTH
Category | Monthly USD | Annual USD | Ceiling | Status | Notes
Hosting (Hetzner CX31) | $20 | $240 | $1,200/mo total | ACTIVATE | 40% cheaper than DO equivalent
M365 (hybrid Standard+Basic) | $55–75 | $660–900 | See staffing budget | ACTIVATE | Lock in before 01 Jul 2026 price rise
Claude AI Pro (×2) | $40 | $480 | AI sub-ceiling | ACTIVATE | CEO + Dev Lead
GitHub Copilot Business (×2) | $38 | $456 | AI sub-ceiling | ACTIVATE | CausewayGrp org billing
WhatsApp Business API | $40 | $480 | Comms budget | ACTIVATE | 500 conversations/month
Starlink Business | $140 | $1,680 | BCP — non-cuttable | PROCURE | Insurance for Aden connectivity
Other SaaS (Canva, Jira, etc) | $13–30 | $156–360 | Within ceiling | ACTIVATE | Canva Pro, Jira free
TOTAL TECH OPEX (tools only) | ~$346–396 | ~$4,152–4,752 | Ceiling: $1,200 | WITHIN CEILING | Excludes developer salaries

## 🗺️ 48M RWP
🗺️ KAYAN 48-MONTH ROLLING WORK PLAN — April 2026 → March 2030 ¦ KAY-TECH-MASTER-OS-001 v1.0
LOCK: No Go-Live target may change without CEO written approval. May 1 2026 is non-negotiable. Budget phase ceilings from KAY-TECH-OS-008 v5. All owners accountable via weekly Thursday delivery reports. Status must be updated every Friday.
# | Month | Date | Deliverable / Milestone | Owner | Budget USD | Status | Phase | Notes / Risk
1 | M1 | Apr 2026 | [CRITICAL] Lead Developer (Mustafa) brief delivered — this OS signed off | CEO | $0 | IN PROGRESS | P1 | This workbook is the brief. CEO distributes Apr 16.
2 | M1 | Apr 2026 | [CRITICAL] GitHub CausewayGrp org — Kayan repo created, CEO owner access confirmed | Dev Lead | $0 | IN PROGRESS | P1 | MaherFSF must have owner-level access before any commit
3 | M1 | Apr 2026 | [CRITICAL] Development environment live — Docker Compose, local DB, CI/CD pipeline | Dev Lead | $0 | IN PROGRESS | P1 | Sprint Plan confirmed this was done by Mar 4
4 | M1 | Apr 2026 | Microsoft 365 subscriptions purchased — annual billing, all mailboxes active | CEO | $0 | PENDING CEO | P1 | Lock in before Jul 1 price increase. Estimated $55-75/month.
5 | M1 | Apr 2026 | All developer accounts created: @kayanwork.com email, GitHub, Jira, Figma | Dev Lead | $0 | PENDING M365 | P1 | Cannot activate until M365 live
6 | M1 | Apr 2026 | Hetzner CX31 VPS provisioned — Docker, Nginx, SSL, Cloudflare DNS configured | Dev Lead | $20/mo | PLANNED | P1 | Replace DigitalOcean for new builds. CauseWay stays on DO.
7 | M1 | Apr 2026 | Bitwarden self-hosted deployed on Hetzner — all staff added, shared vaults created | Dev Lead | $0 | PLANNED | P1 | Eliminates credential sharing via WhatsApp immediately
8 | M1 | Apr 2026 | YETO Observatory: Register 8 free API keys (ACLED, FAO, ILO, Comtrade, IPC, UNCTAD, WHO, UNESCO) | CEO | $0 | CRITICAL OVERDUE | P1 | Each 5-10 mins. Unlocks 5,000+ data points. Do TODAY.
9 | M1 | Apr 2026 | Office VLAN network design finalized — 5 VLANs mapped, Omada gear ordered | Ops+Dev1 | $540 | PLANNED | P1 | Router + Switch + 3 APs. Cannot open office without this.
10 | M1 | Apr 2026 | GitHub Copilot Business activated — 2 developer seats under CausewayGrp org | Dev Lead | $38/mo | PLANNED | P1 | $38/month total. IP indemnity. No training on Kayan code.
11 | M1 | Apr 2026 | kayanwork.com: Home + Services + About pages complete in staging | Dev 2 | $0 | IN PROGRESS | P1 | Arabic RTL primary. Lighthouse ≥ 80 in staging.
12 | M1 | Apr 2026 | Platform: Database schema + auth module (JWT + RBAC 5 roles) working in staging | Dev 1 | $0 | IN PROGRESS | P1 | Modules 1 (Client Portal) + 6 (Admin/RBAC) foundation
13 | M1 | Apr 2026 | Kayan CCTV system installed — 8 cameras + NVR, 30-day recording | Ops | $500 | PLANNED | P1 | Hikvision recommended. Cannot open office without.
14 | M1 | Apr 2026 | Starlink Business hardware installed — failover routing tested | Ops | $500+$140/mo | PLANNED | P1 | BCP critical. Cannot operate without redundant internet.
15 | M2 | May 2026 | ⭐ DAY-1 GO-LIVE: 01 May 2026 — kayanwork.com + platform.kayanwork.com LIVE | ALL | $0 | TARGET | P1 | Non-negotiable. All 11 modules must pass QA before this date.
16 | M2 | May 2026 | [QA GATE] Legal survivability pass: Privacy Policy + T&C live, AML/KYC gate active | CEO + Legal | $0 | PLANNED | P1 | Counsel sign-off required. No go-live without this.
17 | M2 | May 2026 | [QA GATE] Audit readiness pass: append-only log, Excel export, dual-approval queue in code | Dev 1 | $0 | PLANNED | P1 | No go-live without this. Zero exceptions.
18 | M2 | May 2026 | [QA GATE] Adoption readiness: Arabic RTL on Chrome/Safari/Firefox mobile confirmed | Dev 2 | $0 | PLANNED | P1 | Native Arabic speaker review required.
19 | M2 | May 2026 | [QA GATE] Aden resilience: load test 50 concurrent users on 3G simulation. Passes. | Dev 1 | $0 | PLANNED | P1 | Lighthouse ≥ 80 mobile. PWA installable on Android.
20 | M2 | May 2026 | First 3 client SOWs active with 100% funded escrow | CEO + Ops | $0 | TARGET | P1 | Revenue starts. Escrow gate enforced from Day-1.
21 | M2 | May 2026 | 10 pre-verified T2 talent in registry before Day-1 | Ops Admin | $0 | PLANNED | P1 | No talent = no delivery. Recruitment starts Week 1.
22 | M2 | May 2026 | Ready Products catalog live on /services page — first 8 products listed | Dev 2 + CEO | $0 | PLANNED | P1 | Website-in-14-days, Brand Pack, Translation, Landing Page...
23 | M2 | May 2026 | ICT Ops Intern onboarded — Aden, $40/month, 6-month contract signed | HR + Dev | $40/mo | PLANNED | P1 | KAY-CON-006 contract. IT onboarding SOP executed.
24 | M2 | May 2026 | SharePoint staff portal Phase 1 live — 6 sections, all staff onboarded with SSO | Dev 1 | $0 | PLANNED | P1 | All staff have @kayanwork.com + access before Day-1.
25 | M2 | May 2026 | First Power Automate e-approval flow live: Payment Approval chain | Dev 1 | $0 | PLANNED | P1 | Replaces WhatsApp approvals. Full audit trail.
26 | M2 | May 2026 | space.kayanwork.com Hub booking module — desk + room booking live | Dev 1+2 | $0 | PLANNED | P1 | Enables Hub revenue stream from Day-1.
27 | M2 | May 2026 | ICT Security Policy (KAY-ICT-SEC-001) issued and acknowledged by all staff | Dev Lead | $0 | PLANNED | P1 | 2FA enforced. BitLocker verified on all devices.
28 | M3 | Jun 2026 | Full website complete — all 8 pages live, bilingual, Lighthouse ≥ 80 | Dev 2 | $0 | PLANNED | P1 | Includes: Contact, Talent, Clients, Careers, Impact pages
29 | M3 | Jun 2026 | All 11 app modules in production — end-to-end cycle tested: register→SOW→escrow→milestone→payout | Dev 1+2 | $0 | PLANNED | P1 | Full cycle test with real (internal) test transaction.
30 | M3 | Jun 2026 | First external security audit (penetration test) | CEO + Dev | $300 | PLANNED | P1 | Budget $300-500. Results reviewed within 30 days.
31 | M3 | Jun 2026 | impact.kayanwork.com launched — SDG metrics, Endowment tracker, Kayan Score data | Dev 2 | $0 | PLANNED | P1 | For donors, investors, and press. SEO value.
32 | M3 | Jun 2026 | All 25 ICT policy documents drafted and issued | Dev Lead + CEO | $0 | PLANNED | P1 | See DOCS INDEX tab. 25 docs in 8 weeks.
33 | M3 | Jun 2026 | Frontend Dev Intern onboarded — Aden, $40/month | HR | $40/mo | PLANNED | P1 | Frees Dev 2 for architecture tasks
34 | M3 | Jun 2026 | Platform: 50 registered users (clients + talent combined) | CEO + Ops | $0 | TARGET | P1 | Marketing activation begins May 1.
35 | M3 | Jun 2026 | First Ready Product commission fulfilled: Website-in-14-days delivered | Dev 2 + team | Revenue | PLANNED | P1 | Revenue proof-of-concept for Ready Products line
36 | M4 | Jul 2026 | Academy LMS platform live — course catalog, enrollment, certificate generation | Dev 1+2 | $800 | PLANNED | P1 | 10 courses (C001-C010) from Academy OS.
37 | M4 | Jul 2026 | staff.kayanwork.com Phase 2 — branded login, SSO, role-based modules | Dev 1 | $300 | PLANNED | P1 | CEO + HR + Finance dashboard views
38 | M4 | Jul 2026 | Leave approval Power Automate flow live — full HR digital approvals | Dev 1 + HR | $0 | PLANNED | P1 | Included in M365. No extra cost.
39 | M4 | Jul 2026 | First Academy cohort enrolled — minimum 10 students, 6-week cohort | Acad. Coord. | $0 | TARGET | P1 | Revenue: $100-300/student × 10 = $1,000-3,000
40 | M4 | Jul 2026 | Platform: 200 registered users milestone | CEO | $0 | TARGET | P1 | Trigger for marketing campaign review
41 | M4 | Jul 2026 | Kayan Score algorithm v1 live — scoring based on verified data points | Dev 1 | $0 | PLANNED | P2 ENTRY | Composite: completion(40%) + satisfaction(30%) + tier(15%) + income(10%) + disputes(5%)
42 | M5 | Aug 2026 | ⭐ Yeto Talent Marketplace MVP live — yeto.kayanwork.com | Dev 1+2 | $2,800 | PLANNED | P2 | Profiles, AI matching, ratings. NOT the YETO Yemen observatory.
43 | M5 | Aug 2026 | Bidding Module live — brief posting, competitive bids, escrow gate integration | Dev 1 | $1,900 | PLANNED | P2 | Anonymous bids until award. Prevents platform bypass.
44 | M5 | Aug 2026 | Backend Dev Intern onboarded — Cairo, Egypt, $50/month | HR | $50/mo | PLANNED | P2 | Egypt talent pool for backend support
45 | M5 | Aug 2026 | ai.kayanwork.com/match — AI talent matching endpoint via Claude API live | Dev 1 | $0+API | PLANNED | P2 | Inputs: project brief → outputs: ranked talent list with scores
46 | M5 | Aug 2026 | Ready Products: 16 products listed, 5+ commissions fulfilled | Dev 2 + CEO | Revenue | PLANNED | P2 | Website, Brand, Translation, App, Landing Page...
47 | M6 | Sep 2026 | api.kayanwork.com gateway live — Phase 2 partner integrations enabled | Dev 1 | $0 | PLANNED | P2 | INGO portals, university systems, enterprise procurement
48 | M6 | Sep 2026 | Mobile app (React Native PWA wrapper) — installable on Android and iOS | Dev 1+2 | $1,500 | PLANNED | P2 | Core flows offline: project view, deliverable upload, Kayan Score
49 | M6 | Sep 2026 | Platform: 500 monthly active users milestone | CEO | $0 | TARGET | P2 | Triggers SaaS pricing review and investor update
50 | M6 | Sep 2026 | Kayan Card digital issuance live — verified freelancers issued digital card | Dev 1+2 | $0 | PLANNED | P2 | Tadamon Bank prepaid partnership — Kayan Card physical/digital
51 | M6 | Oct 2026 | ⭐ 6-MONTH ICT STAFFING REVIEW — Oct 15, 2026 | CEO + HR | $0 | MILESTONE | P1→P2 | CTO hire? Dev conversions? Intern outcomes? Budget vs actual?
52 | M7 | Oct 2026 | ICT capacity building programme Q4 2026 launched — 5 modules for all staff | Dev Lead | $90 | PLANNED | P2 | M365, SharePoint, Cyber, E-approvals, AI Tools
53 | M7 | Oct 2026 | Kayan Market full launch — self-serve gated freelancer marketplace | Dev 1+2 | $2,000 | PLANNED | P2 | 15% take rate. Verified talent only. Escrow-gated.
54 | M8 | Nov 2026 | Power BI / Looker Studio dashboards — CEO + Finance live data | Dev 1 + Fin | $0 | PLANNED | P2 | P&L in 5 minutes. Connected to platform DB + SharePoint.
55 | M9 | Dec 2026 | Kayan Studio launched — pre-assembled creative/tech pods for enterprise | CEO + Dev | $1,500 | PLANNED | P2 | 8-week sprint delivery model. Studio marketplace on platform.
56 | M10 | Jan 2027 | ICT Learning Plan Q1 2027 launched — intermediate modules (Excel, Power BI, Dev upskilling) | Dev Lead | $300 | PLANNED | P2 | Excel for non-finance, Power BI, DevOps for interns
57 | M12 | Mar 2027 | Annual security audit (Year 1) — full penetration test | CEO + Dev | $500 | PLANNED | P2 | Mandatory annually. Report to CEO + board.
58 | M13 | Apr 2027 | Yeto v2 — AI matching enhancements, team recommendation engine | Dev 1 | $2,000 | PLANNED | P2 | Advanced matching: team composition, Kayan Score weighting
59 | M14 | May 2027 | Enterprise client portal — dedicated dashboard for retainer clients | Dev 1+2 | $1,500 | PLANNED | P2 | Studio clients, INGO partners, government access
60 | M15 | Jun 2027 | CTO hire decision finalized — hire or extend CEO interim | CEO | $0 | MILESTONE | P2 | Based on revenue trajectory and platform complexity
61 | M18 | Sep 2027 | ⭐ PHASE 2 COMPLETE — Platform v1 fully featured, 1,000+ users | CEO | $0 | MILESTONE | P2→P3 | All Phase 2 deliverables signed off. Phase 3 plan locked.
62 | M19 | Oct 2027 | White-label Hub-in-a-Box SaaS — licensing to other coworking spaces | CEO + Dev | $5,000 | PLANNED | P3 | Phase 3 opens new revenue line: SaaS licensing
63 | M20 | Nov 2027 | Advanced analytics + donor reporting module | Dev 1+2 | $3,000 | PLANNED | P3 | SDG metrics, impact reports, evidence for UN/INGO funding
64 | M22 | Jan 2028 | AI-assisted talent matching v2 — vector embeddings, contextual scoring | Dev 1 | $4,000 | PLANNED | P3 | Differentiator. Proprietary data asset.
65 | M24 | Mar 2028 | Egypt expansion — Kayan Hub Cairo infrastructure planning | CEO | $0 | PLANNED | P3 | Technical requirements for Hub-in-a-Box Egypt replication
66 | M25 | Apr 2028 | Multilingual expansion — French and Somali consideration | Dev Team | $3,000 | PLANNED | P3 | MENA + Horn of Africa market expansion
67 | M30 | Sep 2028 | Open API for INGOs + government integration | Dev 1+2 | $4,000 | PLANNED | P3 | Partnership API. Revenue: per-call or subscription licensing.
68 | M36 | Mar 2029 | ⭐ PHASE 3 COMPLETE — SaaS layer operational | CEO | $0 | MILESTONE | P3→P4 | Revenue includes: SaaS licensing, API fees, Studio retainers
69 | M37 | Apr 2029 | Regional replication dashboard — multi-Hub management | Dev Team | $5,000 | PLANNED | P4 | Govern Aden + Cairo + any new Hubs from single admin
70 | M40 | Jul 2029 | Kayan Ventures portfolio management tools | CEO + Dev | $4,000 | PLANNED | P4 | Investment tracking, cap table management, portfolio updates
71 | M42 | Sep 2029 | ISO 27001 readiness assessment | CEO + Sec | $2,000 | PLANNED | P4 | Prerequisite for enterprise contracts and Series A
72 | M43 | Oct 2029 | Full data warehouse + BI dashboard — platform analytics | Dev 1+2 | $6,000 | PLANNED | P4 | Snowflake or BigQuery. Investor-grade analytics.
73 | M44 | Nov 2029 | Series A data room + investor portal live | CEO | $3,000 | PLANNED | P4 | Secure access for investor due diligence
74 | M48 | Mar 2030 | ⭐ PHASE 4 COMPLETE — Platform at scale, Series A ready | CEO | $0 | MILESTONE | P4 | $1M+ ARR target. Regional footprint. Investor-grade compliance.
R | Monthly | Every month | Weekly delivery reports (every Thursday, every month) | Dev Lead | $0 | RECURRING | All | CEO reviews within 24h. Non-response = approved.
R | Monthly | Every month | Monthly subscription cost review — vs budget ceiling | CEO | $0 | RECURRING | All | Any SaaS > $100/mo needs written ROI justification
R | Monthly | Every month | Monthly backup restore test — verify backup integrity | Dev 1 | $0 | RECURRING | All | Log result in SharePoint. Failed test = immediate action.
R | Quarterly | Every quarter | Quarterly ICT OKR review — platform KPIs vs targets | CEO | $0 | RECURRING | All | Feed into investor updates and board reporting
R | Annual | Every year | Annual external security audit (penetration test) | Dev Lead + CEO | $300-500 | RECURRING | All | Budget: $300-500. Mandatory from Year 1.

## 🌐 PLATFORMS
🌐 PLATFORM ECOSYSTEM — All 8 Platforms + Domain Architecture + 11 App Modules
8 KAYAN PLATFORMS — DOMAIN MAP
Platform | Subdomain | Purpose | Phase | Go-Live | Dev Owner
kayanwork.com | kayanwork.com | Public website — 8 pages bilingual. Trust-first narrative. Client + talent acquisition gate. | 1 | 01 May 2026 | Dev 2
Managed Delivery Platform | platform.kayanwork.com | Client intake → SOW → Escrow gate → Pod delivery → QA → net fee extraction. Core revenue engine. | 1 | 01 May 2026 | Dev 1
Hub Booking | space.kayanwork.com | Desk + room booking, membership, QR check-in, occupancy dashboard, event calendar. | 1 | 15 May 2026 | Dev 1+2
Volunteers Portal | volunteers.kayanwork.com | FAEAN volunteer registration, availability, assignment tracker, impact badges, community leaderboard. | 1 | 01 May 2026 | Dev 2
Impact Dashboard | impact.kayanwork.com | SDG metrics, Endowment tracker, Kayan Score data — for donors, investors, press. | 1 (Month 3) | 01 Aug 2026 | Dev 2
Admin Panel | admin.kayanwork.com | Full RBAC admin: all clients, projects, escrow, revenue, audit trail, dual-approval queue. | 1 | 01 May 2026 | Dev 1
Academy LMS | academy.kayanwork.com | Course catalog, enrollment, cohort management, attendance, certificate generation (branded PDF + QR). | 2 | 01 Jul 2026 | Dev 1+2
Yeto Talent Marketplace | yeto.kayanwork.com | Talent profiles, AI matching, competitive bidding, ratings, Kayan Card. Talent marketplace vertical. | 2 | 01 Aug 2026 | Dev 1+2
Bidding Module | platform.kayanwork.com/bid | Client posts briefs; talent bids; Kayan shortlists; awarded bid routes through escrow gate. | 2 | 01 Aug 2026 | Dev 1
API Gateway | api.kayanwork.com | Phase 2+ partner integrations: INGO portals, university systems, enterprise procurement. | 2 (M6+) | Oct 2026 | Dev 1
Staff Portal | staff.kayanwork.com | Internal: HR, finance, dashboards, leave, payslips, policies. Ph1=SharePoint; Ph2=branded. | 1 (P1=SP) | 30 Apr 2026 | CEO+Dev1
11 MANDATORY WEB APP MODULES — MUST PASS QA BEFORE 01 MAY 2026
Module | Name (AR/EN) | Key Features | Who It Serves | QA Gate | Status
M01 | Client Portal / بوابة العملاء | Company registration + KYC; Project intake (SOW builder via AI); Ready product catalog browser; Escrow deposit + funding status; Delivery tracking; Invoice + receipt export | Clients | AML/KYC gate active; SOW generation working; Escrow ledger accurate | IN PROGRESS
M02 | Talent Portal / بوابة المواهب | Freelancer registration + consent; Micro-specialization tagging (40+ tags); Kayan Score visibility; Active task board + deliverable upload; Payment history; Kayan Card dashboard | Talent/Freelancers | Consent stored with timestamp+IP; Score calculated; Payment history accurate | IN PROGRESS
M03 | Volunteers / المتطوعون | Volunteer registration + skills; Availability calendar; Assignment + hours tracker; Impact badge earning; Volunteer portfolio export; Community leaderboard | Volunteers, NGOs | Registration complete; Assignment tracker working; Badges issue correctly | PLANNED
M04 | Kayan Hub / كيان هَب | Space booking (desk/room/day); Membership subscription + billing; Check-in QR system; Occupancy real-time dashboard; Event calendar management; Member directory (opt-in) | Hub Members | Booking confirmed → escrow-gated; QR check-in works; Capacity accurate | PLANNED
M05 | Academy / كيان أكاديمي | Course catalog + enrollment; Cohort management + scheduling; Attendance + progress tracking; Certificate generation (PDF + unique QR verification code); Trainer dashboard; Revenue reporting | Students, Talent | Certificate generates correctly with QR; Revenue reported accurately | PLANNED
M06 | Admin & RBAC / الإدارة | Role-based access control (5 roles: Admin, Finance, Ops, Client, Talent); Full audit trail on all critical actions; Dual-approval payment queue; Export-first (Excel/CSV all registers); Sanctions screening; Financial dashboard + alerts | Kayan Staff | Audit trail append-only and immutable; Dual-approval enforced in DB; All exports work | IN PROGRESS
M07 | Escrow Engine / محرك الضمان المالي | Escrow deposit receipt (liability posting); Milestone release trigger; Net fee extraction (20%); 2% QA holdback; Immutable payment ledger; Payout disbursement + record | CEO, Finance | Zero bypass possible at DB level; Ledger balances exactly; Fee calculated correctly | IN PROGRESS
M08 | SOW Builder / منشئ اتفاقية العمل | SOW required fields form (scope, timeline, budget, milestones, acceptance criteria); AI-assisted draft via Claude API; Dual approval before sending to client; Signed SOW archived in SharePoint; Cannot be modified after escrow funded | CEO, Ops Admin | SOW generates correctly; AI draft usable; Archive complete; Lock-after-funding enforced | PLANNED
M09 | KYC + AML Screening / التحقق من الهوية | Client + talent ID verification; Sanctions screening (OFAC SDN, UN, EU, UK lists); AML risk scoring; Ongoing monitoring flags; Manual review queue for CEO | CEO, Legal, Ops | All new users screened; Blocked users cannot activate; 10-year AML record retention | PLANNED
M10 | Notifications + Comms / الإشعارات | Email (Resend/M365); WhatsApp Business API (Yemen clients); In-app notifications; Milestone alert triggers; Dispute notifications; 48-hour silence = acceptance rule enforced | All users | Email delivers; WhatsApp sends; In-app notifications display; Silence rule triggered correctly | PLANNED
M11 | Analytics + Reporting / التقارير | Platform KPI dashboard; GMV, Net Fee, MAU tracking; Export-first: all data to Excel/CSV; Impact metrics (SDG); Donor reporting; Investor pack generation | CEO, Finance, Donors | KPIs calculate correctly; Exports accurate; Investor-ready reports generate | PLANNED

## 🛍️ READY PRODUCTS
🛍️ READY PRODUCTS CATALOG — Fixed-Scope, Fixed-Price Deliverables for Immediate Commission
CONCEPT: Ready Products are pre-designed, fixed-scope deliverables that clients can commission instantly without a custom SOW — the lowest-friction entry point to the Kayan ecosystem. Priced for accessibility. Commissioned via one-click on /services page. Each product routes through escrow gate. No work starts before 100% payment.
Product Name | Category | Days | Price USD | Take Rate | Kayan Net | What's Included (summary) | What's Excluded | Delivery Stack | Status
Website in 14 Days (6-page bilingual AR/EN) | Website | 14 days | $800 | 20% | $640 | Home, About, Services, Contact, Privacy, ToS. Mobile-first, Lighthouse ≥ 80, RTL, SEO meta. Hosting setup. | Custom backend, e-commerce, user auth. Content writing. | Next.js + Netlify/Vercel | AVAILABLE
Landing Page (1-page, conversion-optimised) | Website | 7 days | $400 | 20% | $320 | Single-page: hero, features, CTA, contact form. Bilingual. Mobile-first. Google Analytics. | Ongoing maintenance. Content writing. Ad campaigns. | Next.js + Netlify | AVAILABLE
E-commerce Website (up to 50 products) | Website | 21 days | $2,500 | 20% | $2,000 | Product catalog, cart, checkout, order management, bilingual, mobile-first, payment integration. | Content writing. Product photography. Arabic translation beyond setup. | Next.js + Shopify/Stripe | AVAILABLE
Custom CMS Website (up to 10 pages) | Website | 21 days | $1,500 | 20% | $1,200 | 10-page CMS-driven site (client editable). Blog, news, events. Bilingual. SEO foundation. | E-commerce, payments, user registration. | Next.js + Directus CMS | AVAILABLE
NGO / Donation Platform | Website | 21 days | $2,500 | 20% | $2,000 | Donation flow, project showcase, impact reporting, volunteer registration, bilingual, GDPR-aligned. | Custom backend integrations. Ongoing content. | Next.js + Directus + Stripe | AVAILABLE
Booking / Reservation System | Web App | 14 days | $1,500 | 20% | $1,200 | Online booking with calendar, availability, confirmation email, admin dashboard, payment. Bilingual. | Custom integrations. Content. Marketing. | Next.js + NestJS + PostgreSQL | AVAILABLE
Corporate Dashboard / Intranet | Web App | 21 days | $2,000 | 20% | $1,600 | Staff portal with login, dashboards, document library, leave tracker, news feed. RBAC. | Payroll integration. Custom ERP links. | Next.js + NestJS + PostgreSQL | AVAILABLE
Mobile App MVP (React Native / PWA) | Mobile App | 30 days | $3,500 | 20% | $2,800 | Core flows: registration, profile, feed/listing, push notifications, offline mode. Bilingual. iOS + Android. | Custom backend. Third-party API integrations beyond 2. | React Native + NestJS | AVAILABLE
Event Management System | Web App | 14 days | $1,800 | 20% | $1,440 | Event listing, registration, ticketing, check-in QR, attendee management, bilingual. | Livestreaming. Complex payment splits. | Next.js + NestJS + PostgreSQL | AVAILABLE
Brand Identity Package | Design | 7 days | $500 | 25% | $375 | Logo (3 concepts, 2 revisions), colour palette, typography, business card, letterhead, brand guide PDF. | Social media templates. Packaging. Photography. | Canva Pro + Figma | AVAILABLE
Social Media Setup Package | Design | 5 days | $300 | 25% | $225 | Profile optimization (3 platforms), cover photos, 10 branded post templates, content calendar template. | Ongoing management. Ad spend. Content writing. | Canva Pro | AVAILABLE
Monthly Social Media Management | Service | Ongoing | $300/mo | 25% | $225/mo | 12 posts/month (Arabic primary), scheduling, community management, monthly performance report. | Ad spend. Photography. Video production. | Canva Pro + Buffer | AVAILABLE
Business Plan Document | Document | 7 days | $400 | 20% | $320 | Full business plan: executive summary, market analysis, operations, financial projections (3-year). Bilingual. | Financial model Excel. Legal advice. | Claude AI + Word | AVAILABLE
Pitch Deck (investor ready) | Document | 5 days | $350 | 20% | $280 | 10-15 slide deck: problem, solution, market, model, traction, team, ask. Bilingual. Branded. | Financial model. Legal due diligence. | Claude AI + Canva | AVAILABLE
Arabic-English Translation | Translation | 3 days | $25/1k words | 30% | $17.5/1k | Professional translation. Native-level Arabic ↔ English. Proofreading included. Kayan QA verified. | Interpretation. Certified legal translation. | Claude AI + Human QA | AVAILABLE
Certified Document Translation | Translation | 5 days | $80/page | 30% | $56/page | Certified Arabic-English translation with Kayan QA stamp. Suitable for legal and official use. | Notarisation. Court-certified translations. | Human translator + QA | AVAILABLE
SEO Foundation Package | Digital Mktg | 10 days | $600 | 20% | $480 | Keyword research (AR+EN), on-page SEO for up to 10 pages, Google Search Console setup, Sitemap, Schema.org markup. | Ongoing SEO. Link building. Paid ads. | Manual + SEO tools | AVAILABLE
Monthly Website Maintenance | Service | Ongoing | $150/mo | 25% | $112/mo | Security updates, plugin updates, uptime monitoring, monthly performance report, 2h minor edits/month. | Major redesigns. New features. Content creation. | Varies by stack | AVAILABLE
WhatsApp Business Setup | Setup | 3 days | $250 | 25% | $187 | WhatsApp Business API setup, welcome flows, FAQ automation, integration with website contact form. | Ongoing management. Content. API fees. | WhatsApp API + Make/Zapier | COMING SOON
E-Approval System (internal) | Web App | 10 days | $800 | 20% | $640 | Custom Power Automate approval flows (up to 5 workflows), SharePoint integration, Teams notifications, audit trail. | M365 licensing. Training beyond 2 hours. | Power Automate + M365 | AVAILABLE
PIPELINE: Arabic Content Writing (5 posts) $150 ¦ Data Dashboard Build $1,200 ¦ Chatbot Integration $600 ¦ API Integration $500 ¦ Custom Database $1,500 — add as team capacity grows

## 👥 DEV TEAM
👥 DEV TEAM ACCOUNTABILITY — Mustafa + Dev 2 + Interns ¦ Rules, Sprint Log, Reviews
TEAM REGISTER
Name/Role | Code | Contract | Location | Kayan Cost/Mo | GitHub | Reports To | Status
Maher Farea — CEO / Interim CTO | CEO/CTO | Founder | Aden/Remote | N/A — Founder | MaherFSF | Board | ACTIVE
Mustafa Haney — Lead Developer (Dev 1) | DEV-LEAD | EGP 13,500/mo, Feb–Aug 2026. 50/50 Kayan/CauseWay split. | Cairo, Egypt | ~$200/mo (Kayan share) | matrix1912@instapay | CEO | ACTIVE
Dev 2 — Frontend Developer | DEV-2 | Contract TBC | Remote | TBD | github.com/CausewayGrp | CEO | ACTIVE
ICT Ops Intern (recruiting) | INTERN-ICT | $40/month, 6-month contract. KAY-CON-006. | Aden, Yemen | $40/month | To be created | Dev Lead | RECRUITING
Frontend Dev Intern (recruiting) | INTERN-FE | $40/month, 6-month contract. KAY-CON-006. | Aden, Yemen | $40/month | To be created | Dev 2 | RECRUITING
Backend Dev Intern (planned Aug 2026) | INTERN-BE | $50/month (Egypt rate). 6-month contract. | Cairo, Egypt | $50/month | To be created | Dev Lead | PLANNED
NON-NEGOTIABLE ACCOUNTABILITY RULES
# | Rule | Frequency | How | Consequence
1 | Weekly Delivery Report | Every Thursday, 17:00 Aden time | Email to m.farea@kayanwork.com AND Teams #dev-updates | Format: (a) completed; (b) next week plan; (c) blockers for CEO decision
2 | CEO Response SLA | Within 24 hours of delivery report | Email or Teams reply | Non-response = plan approved automatically
3 | Missed Reports | Two consecutive missed reports | Formal performance review initiated immediately | Not negotiable. Rule is in the contract.
4 | Production Deployment | Before every production push | Teams message to CEO with: what is being deployed, rollback plan | No exceptions. CEO must acknowledge.
5 | Code Ownership | At all times | CEO (MaherFSF) maintains GitHub owner-level access | No production repo may exist outside CausewayGrp org
6 | Sprint Board | Updated daily | Jira/Trello free tier — stale tickets > 3 days trigger check-in | This is how CEO sees progress without waiting for Thursday
7 | Payment Approval | Monthly | Dual approval: CEO + Finance via Power Automate chain | InstaPay payment only after both approvals in SharePoint
8 | AI Tools Rule | Always | No client data, no financials, no PII into any AI tool | Violation = immediate disciplinary action per KAY-ICT-POL-001
9 | Sprint Performance | Per sprint | ≥ 80% of committed sprint items delivered on time | < 60% for 2 consecutive sprints = formal performance review
10 | 6-Month Review | 15 Oct 2026 | Written review: CTO hire?, intern conversion?, Yeto capacity? | All decisions recorded in SharePoint and emailed to CEO
SPRINT LOG — DELIVERY TRACKER
Sprint | Period | Dev | Key Deliverable | Status | Committed | Delivered | Score % | CEO Note
S1 | Mar 4–17 2026 | Mustafa | CauseWay: DB schema 80%→100%, Directus 25%→100%, frontend wire to backend | COMPLETE | Per sprint plan | Per CauseWay brief | TBC | CauseWay sprint plan confirmed
S2 | Apr 1–14 2026 | Dev 1+2 | Kayan: Platform auth+RBAC, Website Home/Services/About staging | IN PROGRESS
S3 | Apr 15–30 2026 | Dev 1+2 | ALL 11 modules functional staging, QA gates pass, go-live prep | PLANNED
S4 | May 1–15 2026 | Dev 1+2 | Day-1 go-live, first 3 SOWs, Hub booking, Ready Products catalog live | PLANNED
S5 | May 16–31 2026 | Dev 1+2 | Full website 8 pages, Academy pre-build, ICT intern onboarding | PLANNED
S6 | Jun 1–15 2026 | Dev 1+2 | Academy LMS, impact.kayanwork.com, all 25 ICT docs issued | PLANNED

## 📋 WEBSITE SPECS
📋 WEBSITE SPECIFICATIONS — kayanwork.com ¦ 8 Pages ¦ Bilingual AR/EN ¦ Mobile-First
GLOBAL RULES: Arabic RTL primary (loads by default for .ye and GCC IPs). Brand: Deep Teal #0D4F4F + Golden Ochre #C8962E. LCP ≤ 2.5s on 3G. Lighthouse ≥ 80 mobile. Privacy consent before tracking. No stock photos. Trust-first narrative on every page. Dev 2 owns all pages.
Page | URL | Key Sections (from KAY-TECH-OS-008 v5) | Primary Objective | QA Check
Home / الرئيسية | / | Hero (AR headline + EN toggle, 2 CTAs); Trust strip (3 pillars); How it works (3 steps); Services preview (3 cards); Kayan Score preview; Social responsibility (FAEAN/SDG); Footer with Privacy+T&C | Convert skeptical first-time visitor to registered user within 90 seconds | AR RTL on Chrome/Safari/Firefox mobile; LCP ≤ 2.5s 3G; No page mentions price before trust proposition
Services / الخدمات | /services | Managed Delivery (8-step process + escrow diagram); Ready Products catalog (all 20 products with 1-click commission button); Kayan Hub pricing table; Academy course preview; Market Coming Soon; Studio Coming Soon; Kayan Cards | Prospect knows exactly which service they need and takes appropriate action | Ready Products catalog live Day-1; Each product has: name, description, timeline, price, included/excluded, 1-click CTA
For Clients / للعملاء | /clients | How Delivery works (6-step flow); SOW builder preview; Ready product catalog (same as /services); Trust gate explanation; Escrow protection explainer; Case study (Day 2 post-first-project) | Client understands escrow-first model and trusts it enough to register | Escrow explanation clear in Arabic; SOW builder CTA works; KYC gate explains what's needed
For Talent / للمواهب | /talent | Freelancer registration CTA; Micro-specializations (40+ tags display); Kayan Score explained (composite formula visible); Kayan Card programme; FAEAN volunteer opportunity; Income trajectory examples | Talent understands how to qualify, how to earn, and why Kayan is better than direct freelancing | Consent form loads; Micro-specialization tags display correctly RTL; Score formula explained clearly
About / عن كيان | /about | Frontier Economy statement (manifesto); Founding team (4 founders with bios); Legal & governance disclosure (Yemen LLC, registration number, address); Milestones timeline; Compliance credentials (AML/KYC, PSEA, Data Protection) | Establish institutional credibility — critical for INGO and UN partnerships | Legal disclosure shows registration number (when available); Address in Arabic and English; PSEA policy linked
Contact / تواصل | /contact | WhatsApp first (primary Yemen channel); Email: m.farea@kayanwork.com; Address with map; Privacy consent checkbox; GDPR-aligned intake form; Business hours | Convert visitor to conversation. Zero friction. | WhatsApp link opens correct number; Form submits to SharePoint; Privacy consent fires before form submits
Impact / الأثر | /impact | SDG metrics dashboard (live data); Kayan Endowment tracker (0.5% of talent income); Kayan Score aggregate data; Impact reports (downloadable); FAEAN programme stats | Satisfy donor, investor, and partner due diligence requirements | SDG metrics update from platform DB; Endowment calculation correct; Reports downloadable as PDF
Careers / وظائف | /careers | Active job postings (with application form linking to info@kayanwork.com); Internship programme (Yemen $40, Egypt $50); Equal opportunity statement; Kayan culture statement | Talent acquisition pipeline for Kayan team itself | Application form works; Jobs page SEO-indexed; Internship terms clear

## 📱 APP MODULES
📱 11 WEB APP MODULES — Full Specifications ¦ All must QA-PASS before 01 May 2026
BUILD PRINCIPLES — NON-NEGOTIABLE (from KAY-TECH-OS-008 v5 + PPTX)
Principle | Specification
Mobile-first PWA | Platform is installable on Android and iOS. Core flows function offline: view projects, submit deliverables, check Kayan Score. Auto-sync on reconnection.
Bilingual AR/EN | Arabic RTL primary. English LTR toggle. Both in same codebase. AR loads by default for .ye and GCC IPs. All UI elements RTL-validated.
Aden-grade resilience | Works on 3G (simulated Lighthouse 1.6Mbps). Target page weight: < 500KB critical path. Brotli compression. WebP images. LCP ≤ 2.5s.
Export-first fallback | Every operational register exportable to Excel/CSV in one click at all times. If platform is unavailable, Kayan can operate on spreadsheets from last sync.
Immutable audit trail | Every critical action: timestamp, user ID, IP address, action type. Append-only event log. Cannot be deleted. 36-month retention in DB. AML records: 10 years.
RBAC — 5 roles from Day-1 | Admin, Finance, Ops, Client, Talent. No user can access data outside their role. Escrow gate cannot be overridden by any role including Admin.
Dual approval enforcement | All payment release: CEO + Finance digital confirmation. Single-auth blocked at DB level. Every payment event logged in immutable ledger.
No Hawala/crypto | Payments: Tadamon Islamic Bank only. Dual approval enforced in code. This rule is in the Terms of Service and the employment contracts of every developer.
MODULE SPECIFICATIONS
Module + Code | Full Feature List | QA Gate (must PASS before go-live) | Status
M01 — Client Portal | Company registration with KYC form + consent layer ¦ Project intake via SOW builder (AI-assisted via Claude API) ¦ Ready product catalog browser with 1-click commission ¦ Escrow deposit flow (Tadamon Bank + manual gateway) ¦ Funding status tracker ¦ Delivery tracking dashboard with milestone statuses ¦ Invoice generation + receipt export (PDF) ¦ Communication thread per project ¦ Dispute initiation flow | KYC gate active; SOW builder generates correctly; Escrow ledger posts to liability account; Invoice PDF generates; Silence=acceptance rule fires at 48h | IN PROGRESS
M02 — Talent Portal | Freelancer registration + explicit triple consent (data use, comms, KAY-CON-006 terms) — stored with timestamp+IP ¦ Micro-specialization tagging (40+ tags, mandatory) ¦ Kayan Score badge display ¦ Active task board with milestone status ¦ Deliverable upload (files to Cloudflare R2 / MinIO) ¦ Payment history + pending disbursements ¦ Kayan Card dashboard ¦ Portfolio export (PDF) ¦ Availability calendar | Consent stored immutably; Score calculates correctly; Deliverable upload works on 3G; Payment history accurate to cent | IN PROGRESS
M03 — Volunteers Portal | Volunteer registration + skills declaration ¦ Availability calendar with slot management ¦ Assignment creation by Ops Admin ¦ Hours tracker (auto + manual entry) ¦ Impact badge earning (milestone-based) ¦ Volunteer portfolio export ¦ Community leaderboard (opt-in) ¦ FAEAN programme integration ¦ SDG impact tagging per volunteer | Registration complete; Assignment creates correctly; Hours calculate; Badges issue on milestone trigger | PLANNED
M04 — Kayan Hub | Real-time space availability calendar ¦ Desk + room + training hall booking ¦ Membership tier subscription management (day/monthly/annual) ¦ Online payment for bookings ¦ QR check-in system (generates unique QR per booking) ¦ Occupancy real-time dashboard ¦ Event calendar management ¦ Member directory (opt-in toggle) ¦ Café integration (ordering linked to membership) | Booking confirmed → payment collected → QR generated → check-in scans correctly; Double-booking prevented | PLANNED
M05 — Academy LMS | Course catalog with syllabus preview + instructor bio ¦ Enrollment flow: browse → select → pay → access ¦ Cohort management + scheduling ¦ Attendance tracking (per session) ¦ Progress tracking (% complete) ¦ Assessment submission ¦ Branded PDF certificate generation with unique QR verification code ¦ Trainer dashboard with roster ¦ Academy revenue reporting ¦ Talent pipeline — graduates fed into verification registry | Certificate QR verifies correctly; Revenue reports balance; Enrollment → access flow works end-to-end | PLANNED
M06 — Admin & RBAC | 5-role RBAC (Admin, Finance, Ops, Client, Talent) — enforced at DB level ¦ Full admin dashboard: all projects, clients, talent, escrow, revenue ¦ Dual-approval payment queue (cannot release single-auth) ¦ Export-first: all registers to Excel/CSV ¦ Sanctions screening dashboard ¦ Financial KPI dashboard + alerts ¦ User management (create/suspend/deactivate) ¦ System settings management ¦ Audit trail viewer (read-only, no delete) | All 5 roles load correct data only; Dual approval blocks single-auth; All exports generate; Audit trail append-only | IN PROGRESS
M07 — Escrow Engine | Escrow deposit receipt → posts to liability account (NOT revenue) ¦ Milestone release trigger: Ops Admin approval → client 48h silence window → release ¦ Net fee calculation (20%) and extraction ¦ 2% QA holdback (30-day retention) ¦ Immutable payment ledger (append-only event log) ¦ Payout disbursement to talent + record ¦ Refund flow (pre-commencement) ¦ Dispute escrow freeze ¦ Financial reconciliation export | Zero bypass possible at DB — escrow gate cannot be circumvented ¦ Ledger balances exactly ¦ Fee calculation correct ¦ 2% holdback retained for exactly 30 days | IN PROGRESS
M08 — SOW Builder | Structured SOW form: title, scope (deliverables+exclusions+assumptions), timeline (start+milestones+end), budget (total+per-milestone in USD), revision rounds, acceptance criteria ¦ AI-assisted draft via Claude API ¦ CEO and Finance dual review + digital approval ¦ Signed SOW archived in SharePoint ¦ Cannot be modified after escrow is funded (DB lock) ¦ Yemen Commercial Law governing clause auto-inserted ¦ PDF export with Kayan letterhead | SOW generates PDF correctly; AI draft usable quality; Archive to SharePoint confirmed; Lock-after-funding enforced in DB | PLANNED
M09 — KYC + AML | Client + talent ID verification form ¦ Sanctions screening: OFAC SDN, UN consolidated, EU, UK HMT lists ¦ Automated risk scoring (Low/Medium/High/Blocked) ¦ Ongoing monitoring: re-screen on list updates ¦ Manual review queue for CEO (flagged cases) ¦ AML records: 10-year retention ¦ Blocked user cannot activate account ¦ KYC re-verification trigger (annually for active high-value clients) ¦ Compliance export for reporting | All new users screened before activation; Blocked users cannot proceed; 10-year retention in DB; Screening log immutable | PLANNED
M10 — Notifications | Email via Resend (transactional, Arabic-compatible templates) ¦ WhatsApp Business API (primary Yemen channel): booking confirmations, payment alerts, milestone updates ¦ In-app notification bell ¦ Milestone submission → client notification ¦ 48-hour silence rule enforcement (automated timer) ¦ Dispute notification chain ¦ New SOW → dual approval alert ¦ Escrow funded → team activation alert ¦ Weekly CEO summary email | Email delivers in Arabic correctly; WhatsApp sends with correct content; 48h timer triggers correctly; No duplicate notifications | PLANNED
M11 — Analytics | Platform KPI dashboard: GMV, Net Fee, MAU, DAU, escrow positions, fill rate, NPS ¦ Revenue waterfall chart ¦ Export-first: all data to Excel/CSV one-click ¦ SDG impact metrics (employment, income generated, training hours) ¦ Donor-ready impact report (PDF auto-generation) ¦ Investor pack data (monthly) ¦ Kayan Score aggregate trends ¦ Search/filter by date range, service type, talent tier ¦ API endpoint for impact.kayanwork.com | All KPIs calculate correctly; Excel export matches DB; Impact reports generate; Investor data accurate | PLANNED

## 💰 BUDGET & ROI
💰 ICT & PLATFORM BUDGET — CAPEX + OPEX + ROI ¦ Ceiling: $1,200/month tech sub-budget
CAPEX — ONE-TIME INVESTMENTS
Item | Category | Budget USD | Actual USD | Priority | Notes
Platform Development (11 modules + website) | Platform Dev | $8,000–12,000 |  | CRITICAL | Primary revenue enabler. Internal dev reduces cost.
4× Staff Laptops (i5, 8GB, 256GB SSD) | Hardware | $1,200 |  | CRITICAL | Pre Day-1. Refurbished ThinkPad saves 30%.
Network (TP-Link Omada: Router + Switch + 3 APs) | Networking | $440 |  | CRITICAL | Managed VLAN setup. 5 VLANs for Staff/Member/IoT/CCTV/Mgmt.
UPS — Network rack + 2× workstation units | Power | $380 |  | CRITICAL | Protects $10K+ of equipment during Aden power cuts.
CCTV — 8 cameras + 4TB NVR (Hikvision) | Security | $500 |  | CRITICAL | 30-day recording. VLAN 40 isolated. CEO + Ops keys only.
Starlink Business hardware | Connectivity | $500 |  | CRITICAL | BCP. Monthly $140 ongoing. Cannot operate without redundancy.
2× Laser MF Printers | Hardware | $400 |  | HIGH | HP LaserJet. $0.01/page vs $0.05/inkjet.
Reception Display TV (43-55") | Hardware | $280 |  | HIGH | Kayan brand screen at reception.
2× External HDD Backup (4TB Seagate IronWolf) | Storage | $200 |  | HIGH | One on-site encrypted, one off-site rotation.
Penetration Test (Year 1) | Security | $300 |  | HIGH | External consultant. Results to CEO within 30 days.
Office cabling + ICT setup | Infrastructure | $400 |  | HIGH | Structured cabling. Done properly = no rework.
MONTHLY OPEX
Service | Category | USD/Month | Annual | Within Ceiling | Notes
M365 Business Standard (3 seats: CEO, Finance, Dev Lead) | Productivity | $37.50 | $450 | YES | Lock in before Jul 2026 price rise → $14/user
M365 Business Basic (2-4 seats: other staff) | Productivity | $12–28 | $144–336 | YES | $6/user. Upgrade to Standard selectively only.
Claude AI Pro × 2 users | AI | $40 | $480 | YES | CEO + Dev Lead. Team plan cheaper at 3+ users.
GitHub Copilot Business × 2 devs | AI/Dev | $38 | $456 | YES | Under CausewayGrp org. IP indemnity included.
Hetzner CX31 VPS | Hosting | $20 | $240 | YES | 8GB RAM, 4 vCPU. 40% cheaper than DO equivalent.
Cloudflare (CDN, DNS, SSL) | Infrastructure | $0 | $0 | FREE | DDoS, CDN, zero-cost SSL. Free tier covers all current needs.
Domain (Cloudflare Registrar) | Infrastructure | $2 | $24 | YES | At-cost pricing. All kayanwork.com subdomains.
WhatsApp Business API | Communication | $40 | $480 | YES | 500 conversations/month. Primary Yemen client channel.
Starlink Business (monthly) | Connectivity | $140 | $1,680 | CAPEX SEPARATE | BCP. Non-negotiable for Aden operations.
Bitwarden (self-hosted on Hetzner) | Security | $0 | $0 | FREE | Password manager. Self-hosted = zero marginal cost.
Canva Pro (1 team account) | Design | $13 | $156 | YES | One account covers all staff. Brand kit loaded.
Jira (sprint board) | Dev Tools | $0 | $0 | FREE | Free for < 10 users. Upgrade only at 10+.
Google Analytics 4 | Analytics | $0 | $0 | FREE | Free forever. GA4.
Figma (UI design) | Dev Tools | $0 | $0 | FREE | Free starter covers current team.
Power Automate (e-approvals) | Workflow | $0 | $0 | FREE | Included in M365 Standard. Replaces Zapier.
Resend (transactional email) | Communication | $0–20 | $0–240 | YES | 3,000 free emails/month. Arabic-compatible.

## 🔧 TOOLS REGISTER
🔧 TOOLS & SUBSCRIPTIONS REGISTER — All SaaS, AI, and Dev Tools
Tool / Service | Category | Plan | USD/Month | Owner | Decision | Notes
Microsoft 365 Business Standard (×3) | Productivity | x3 power users | $37.50 | CEO, Finance, Dev Lead | ACTIVATE — lock in annual billing Jul 2026 | Full desktop Office + Power Automate + Teams
Microsoft 365 Business Basic (×2-4) | Productivity | Per user | $12–28 | Other staff | ACTIVATE | Web Office only — sufficient for ops/admin roles
Claude AI (Anthropic) — Pro ×2 | AI | Pro × 2 users | $40 | CEO + Dev Lead | ACTIVATE IMMEDIATELY | Content, strategy, translation, platform AI features
GitHub Copilot Business — ×2 devs | AI/Dev | Business org | $38 | Dev Lead (CausewayGrp org) | ACTIVATE — under CausewayGrp | IP indemnity. No training on Kayan code. JetBrains support.
Microsoft Copilot Chat | AI | M365 included | $0 extra | All staff | ACTIVE with M365 | AI in Outlook, Teams, Word, Excel — free add-on
Hetzner CX31 VPS | Hosting | Monthly VPS | $20 | Dev 1 | ACTIVATE — new Kayan builds | 8GB RAM 4vCPU 80GB SSD. 40% cheaper than DO.
Cloudflare (CDN + DNS + SSL) | Infrastructure | Free tier | $0 | Dev 1 | ACTIVE | DDoS, CDN, DNS, SSL. Free forever for current scale.
kayanwork.com domain (Cloudflare Registrar) | Infrastructure | Annual renewal | $2/mo equiv. | Dev 1 | ACTIVE | At-cost pricing. All subdomains.
WhatsApp Business API (via BSP) | Communication | Per conversation | $40 | Ops Manager | ACTIVATE | 500 conv/mo. Primary Yemen client channel.
Starlink Business | Connectivity | Business plan | $140 | Ops | PROCURE URGENTLY | BCP. Cannot operate Aden office without redundant internet.
Bitwarden (self-hosted) | Security | Self-hosted free | $0 | Dev 1 | ACTIVATE Week 1 | Deploy on Hetzner in < 2 hours. Eliminates WhatsApp credential sharing.
Canva Pro | Design | 1 team account | $13 | Marketing | ACTIVE | All staff. Brand kit, social graphics, presentations.
Figma | Dev/Design | Starter (free) | $0 | Dev 2 | ACTIVATE | UI/UX design. Free starter covers current team.
Jira (sprint board) | Dev | Free < 10 users | $0 | Dev Lead | ACTIVATE | Sprint tracking, backlog, bug tracking.
Loom | Communication | Starter (free) | $0 | Dev team | ADOPT | Async video for sprint demos. 25 videos/person free.
Google Analytics 4 | Analytics | Free | $0 | Dev 2 | ACTIVE | Website analytics. Free forever.
Power Automate | Workflow | M365 included | $0 | Dev 1 | ACTIVE with M365 | All 20 approval workflows. Replaces Zapier.
Resend (transactional email) | Communication | Free (3K emails/mo) | $0–20 | Dev 1 | ACTIVATE | Arabic templates. Used for platform notifications.
Postman (API testing) | Dev | Free | $0 | Dev 1 | ACTIVATE | API development and documentation. Free forever.
Better Stack / UptimeRobot | Monitoring | Free tier | $0 | Dev 1 | ACTIVATE | Platform uptime monitoring. Alert to CEO WhatsApp.
Microsoft eSignature | Digital Signing | M365 included | $0 extra | CEO | TEST FIRST | Test before paying for DocuSign. Included in Standard.
Notion (knowledge base) | Knowledge | Free up to 10 | $0 | Dev Lead | EXPLORE Phase 2 | Better UX than SharePoint for process documentation.

## ✅ E-APPROVALS
✅ E-APPROVAL WORKFLOWS — All 20 flows on Power Automate + Forms (free with M365)
Approval Type | Approval Chain | Workflow Description | SLA | Ref Doc
Payment < $200 | Staff → Manager → Finance (log) | M365 Form → Power Automate → Manager Teams card → Finance auto-log → SharePoint audit trail | < 24h | KAY-FIN-FRM-001
Payment $200–$1,000 | Staff → Manager → CEO | As above + CEO approval step before release | < 48h | KAY-FIN-FRM-001
Payment > $1,000 | Staff → Manager → CEO + Finance dual | Both CEO and Finance must approve before payment processed. Dual-approval in admin panel. | < 5 days | KAY-FIN-FRM-001 + KAY-GOV-006
Petty Cash (YER ≤ 50K max) | Staff → Cashier → Manager spot-check | M365 Form → auto-log → cashier issues cash → receipt photo uploaded to SharePoint | Same day | KAY-FIN-FRM-003
Invoice Approval | Finance → CEO | Invoice to SharePoint → CEO notified → approves → Finance processes → GL entry | < 48h | KAY-FIN-FRM-002
Leave Request | Staff → Manager → HR | Form → Teams card approval → HR calendar update → leave balance deducted | < 24h | KAY-HR-FRM-003
Overtime Request | Staff → Manager → CEO → Finance | Form → manager hours approval → CEO sign-off → Finance payroll note | < 24h | KAY-HR-FRM-010
New Hire Approval | HR → CEO (→ Board if equity/senior) | Interview scoring form → CEO approves offer → DocuSign/eSign contract → SharePoint archive | < 1 week | KAY-HR-POL-001
Expense Claim | Staff → Manager → Finance → CEO (>$100) | Receipt photo via Form → route by amount → dual approval > $100 → payroll cycle | < 5 days | KAY-HR-FRM-FIN-013
Exit Clearance | All depts + IT last | Exit checklist → each dept signs off row → IT deactivates all accounts within 2h of exit | Last working day | KAY-HR-FRM-012
Purchase Order | Ops → Finance → CEO | PO Form → Finance budget check → CEO approval → PO issued → GRN on delivery → invoice match | < 3 days | KAY-FRM-FIN-005
SOW / Contract Approval | Delivery Mgr → CEO | SOW to SharePoint → CEO reviews → approves → DocuSign to client → signed copy archived | < 24h | KAY-CON-002
New Client Onboarding | Ops → CEO → Legal | Client intake → KYC checklist → AML check → CEO approves → welcome pack → platform account | < 3 days | KAY-CLT-005
New Talent Verification | Talent Team → CEO | Verification pipeline → auto-scoring → CEO spot-reviews borderline → Kayan Card issued → profile activated | < 5 days | KAY-FRM-OPS-003
Incident Report | Any staff → CEO (immediate) | Incident Form → Power Automate immediately alerts CEO + Legal → 72h GDPR clock starts → Trello task | Immediate | KAY-FRM-RSK-001
New User Account | HR → Dev Lead | KAY-ICT-FRM-001 → Dev Lead creates M365 account → permissions set per RBAC → 2FA enforced | Same day as start | KAY-ICT-FRM-001
New Software/Tool Request | Staff → CEO | KAY-ICT-FRM-003 → CEO approves/rejects with reason → activated → subscription register updated | < 3 days | KAY-ICT-FRM-003
Access Level Escalation | Manager → Dev Lead → CEO | Form → Dev Lead security review → CEO approves CONFIDENTIAL access → RBAC matrix updated | < 48h | KAY-ICT-SOP-001
Platform Deployment | Dev → CEO acknowledge → Deploy | Teams message with: what, rollback plan → CEO acknowledges → deploy → post-deploy health check | Same day ack | KAY-ICT-SOP-008
Security Incident | Any staff → CEO (1 hour SLA) | KAY-ICT-FRM-004 → immediate CEO alert → 72h regulatory clock → investigation task created | 1h CEO alert | KAY-ICT-FRM-004

## 🔒 SECURITY
🔒 ICT SECURITY FRAMEWORK — Controls, Compliance, Risk Register
Control / Requirement | Owner | Deadline | Priority
2FA mandatory on all @kayanwork.com accounts — Microsoft Authenticator app ONLY (no SMS) | Dev Lead | Week 2 Apr 2026 | CRITICAL
Full-disk encryption (BitLocker) on all Kayan devices before first use | Dev 1 | Pre Day-1 | CRITICAL
Bitwarden self-hosted deployed — all staff on-boarded, shared vaults created | Dev 1 | Week 1 Apr 2026 | CRITICAL
RBAC matrix documented and implemented — 5 roles, principle of least privilege | Dev 1 | Pre Day-1 | CRITICAL
Microsoft Intune remote wipe configured on all Kayan devices | Dev 1 | Week 2 Apr 2026 | CRITICAL
Data classification applied: CONFIDENTIAL / INTERNAL / PUBLIC — all documents tagged | CEO | Week 3 Apr 2026 | CRITICAL
No client PII, financials, or sensitive data input into any AI tool (KAY-ICT-POL-001) | CEO | Day-1 | CRITICAL
Escrow gate enforced at DB level — zero bypass for any user including Admin | Dev 1 | Pre Day-1 | CRITICAL
Append-only audit log — every critical action logged, cannot be deleted, 36-month retention | Dev 1 | Pre Day-1 | CRITICAL
Payments via Tadamon Bank ONLY — Hawala/crypto absolutely prohibited, enforced in code | Dev 1 + CEO | Pre Day-1 | CRITICAL
VLAN segmentation: Staff/Member/IoT/CCTV/Management — implemented on Omada | Dev 1 + Ops | Pre Day-1 | HIGH
Guest Wi-Fi with 4-hour time limit and monthly password change | Dev 1 | Pre Day-1 | HIGH
WireGuard VPN on Hetzner for all remote admin access — no direct RDP | Dev 1 | Week 4 Apr 2026 | HIGH
Daily automated backup: M365 Exchange/SharePoint + Backblaze B2 | Dev 1 | Week 2 May 2026 | HIGH
Weekly encrypted HDD backup + monthly off-site copy (separate building) | Finance/Dev | Ongoing | HIGH
Quarterly backup restore test — log result in SharePoint | Dev 1 | Quarterly | HIGH
CCTV covering: entrance, reception, café, corridors, meeting rooms — 30-day NVR recording | Ops | Pre Day-1 | HIGH
Network room/cabinet locked — keys: CEO + Dev Lead only | Ops | Pre Day-1 | HIGH
Screen auto-lock: 5 minutes maximum, enforced via Intune policy | Dev 1 | Week 2 | HIGH
Annual external penetration test ($300-500) — results to CEO within 30 days | CEO + Dev | Annual | HIGH
All staff acknowledge ICT policies at onboarding (KAY-ICT-SOP-001 checklist) | Dev Lead + HR | Each new hire | HIGH
AML/KYC screening active for all clients and talent before account activation (OFAC, UN, EU, UK) | Dev 1 | Pre Day-1 | HIGH
Incident response SOP: Detect → Report → Contain → Investigate → Recover → Review | Dev 1 + CEO | Week 5 | MEDIUM
Staff cybersecurity awareness training (phishing simulation 30 days after training) | Dev Lead | Oct 2026 | MEDIUM

## 📑 DOCS INDEX
📑 ICT DOCUMENTS INDEX — All 25 Policies, SOPs, Registers, Forms & Manuals
Code | Title | Type | Owner | Target Date | Version | Status | Notes
KAY-ICT-POL-001 | AI Tools Usage Policy | Policy | CEO | Wk 3 Apr 2026 | v1.0 | DRAFT | Full text in KAY-TECH-OS-008 v7.0 Section 8.2
KAY-ICT-POL-002 | Acceptable Use Policy (AUP) | Policy | Dev Lead | Wk 4 Apr 2026 | v1.0 | DRAFT | Approved software, personal device, internet use rules
KAY-ICT-POL-003 | Remote & Flexible Working Policy | Policy | CEO + HR | Wk 4 Apr 2026 | v1.0 | DRAFT | VPN mandatory, approved devices, working hours expectations
KAY-ICT-SEC-001 | ICT Security Policy (master) | Policy | Dev Lead + CEO | Wk 3 Apr 2026 | v1.0 | DRAFT | 26 controls across 6 domains. Full text in v7.0 Section 8.3
KAY-ICT-SOP-001 | Staff IT Onboarding SOP | SOP | Dev Lead | Wk 3 Apr 2026 | v1.0 | DRAFT | 10-step process. Full detail in User Mgmt tab + v7.0
KAY-ICT-SOP-002 | Staff Exit Deprovisioning SOP | SOP | Dev Lead + HR | Wk 3 Apr 2026 | v1.0 | DRAFT | Account deactivation within 2h of exit. Device return.
KAY-ICT-SOP-003 | Outlook & Email Usage SOP | SOP | CEO + Dev Lead | Wk 2 Apr 2026 | v1.0 | DRAFT | Signature standard, folder, naming, retention, professional use
KAY-ICT-SOP-004 | Backup & Disaster Recovery SOP | SOP | Dev 1 | Wk 4 Apr 2026 | v1.0 | DRAFT | Daily/weekly/monthly schedule, off-site rules, restore test protocol
KAY-ICT-SOP-005 | Incident Response SOP | SOP | Dev 1 + CEO | Wk 5 Apr 2026 | v1.0 | DRAFT | 6 steps: Detect → Report → Contain → Investigate → Recover → Review
KAY-ICT-SOP-006 | Software Procurement & Approval SOP | SOP | CEO + Dev Lead | Wk 4 Apr 2026 | v1.0 | DRAFT | Tool request → CEO approval → activation → register update
KAY-ICT-SOP-007 | Network & Device Maintenance SOP | SOP | Dev Lead | Wk 5 Apr 2026 | v1.0 | DRAFT | Monthly firmware updates, quarterly security scan, annual HW review
KAY-ICT-SOP-008 | Platform Deployment SOP (CI/CD) | SOP | Dev 1 | Wk 3 Apr 2026 | v1.0 | DRAFT | Git workflow, code review gates, staging→production, rollback
KAY-ICT-SOP-009 | E-Approval Workflow Admin SOP | SOP | Dev 1 | May 2026 | v1.0 | PLANNED | How to add/modify Power Automate flows, train users
KAY-ICT-REG-001 | Equipment & Asset Register | Register | Dev Lead + Ops | Wk 2 Apr 2026 | v1.0 | DRAFT | All hardware: serial, purchase date, assigned user, warranty
KAY-ICT-REG-002 | Software & Subscription Register | Register | CEO + Dev Lead | Wk 2 Apr 2026 | v1.0 | DRAFT | All SaaS: name, plan, cost, owner, renewal date (see Tools tab)
KAY-ICT-MAN-001 | Digital Tools Manual (bilingual AR/EN) | Manual | Dev Lead | Wk 4 Apr 2026 | v1.0 | DRAFT | Every tool, purpose, who has access. No passwords. Bilingual.
KAY-ICT-FRM-001 | New User Account Request Form | Form | HR + Dev Lead | Wk 2 Apr 2026 | v1.0 | DRAFT | M365 Form. Captures role, start date, access level required.
KAY-ICT-FRM-002 | IT Support Ticket Form | Form | Dev Lead | Wk 2 Apr 2026 | v1.0 | DRAFT | Microsoft Form → Teams #it-support channel → triage by intern
KAY-ICT-FRM-003 | Software/Tool Request Form | Form | CEO | Wk 3 Apr 2026 | v1.0 | DRAFT | Tool name, cost, purpose, alternatives considered. CEO decision.
KAY-ICT-FRM-004 | Security Incident Report Form | Form | Dev 1 + CEO | Wk 1 Apr 2026 | v1.0 | IN PROGRESS | Power Automate → immediate CEO alert → 72h clock → Trello task
KAY-ICT-FRM-005 | Device Issue / Return Form | Form | Dev Lead | Wk 4 Apr 2026 | v1.0 | DRAFT | Used on exit clearance. Device condition, IT sign-off.
KAY-LEG-015 | Data Protection & Cybersecurity Policy (Legal) | Policy (Legal) | CEO + Legal | Mar 2026 | v1.0 | ISSUED | From legal folder. Foundation for all ICT security policies.
KAY-CMP-003 | Data Protection & Privacy Policy (AR) | Policy (Legal) | CEO | Mar 2026 | v1.0 | ISSUED | Yemeni regulatory compliance. GDPR principles.
KAY-WEB-001 | Website Privacy Policy | Legal/Web | CEO + Legal | Mar 2026 | v1.0 | ISSUED | Full text: kayanwork.com/privacy and KAY-TECH-OS-008 v7.0 S11
KAY-WEB-002 | Website Terms of Service | Legal/Web | CEO + Legal | Mar 2026 | v1.0 | ISSUED | Full text: kayanwork.com/terms and KAY-TECH-OS-008 v7.0 S12

## 👤 USER MGMT
👤 USER MANAGEMENT — RBAC Matrix, Live User Register, Onboarding SOP
ROLE-BASED ACCESS CONTROL MATRIX
ROLE | M365 Email | SharePoint Full | Platform Admin | Finance Data | HR Records | GitHub Repo | Server/VPS | CCTV System
CEO | FULL | FULL | FULL | FULL | FULL | FULL | FULL | FULL
Finance Lead | FULL | READ | READ | FULL | READ | NONE | NONE | NONE
HR Lead | FULL | READ | NONE | READ | FULL | NONE | NONE | NONE
Ops Manager | FULL | READ | LIMITED | READ | READ | NONE | NONE | FULL
Dev Lead (Dev 1) | FULL | READ | ADMIN | READ | NONE | FULL | FULL | NONE
Dev 2 | FULL | READ | LIMITED | NONE | NONE | FULL | LIMITED | NONE
ICT Intern | FULL | READ | NONE | NONE | NONE | LIMITED | NONE | NONE
FE Intern | FULL | READ | NONE | NONE | NONE | LIMITED | NONE | NONE
General Staff | FULL | READ | NONE | NONE | Own only | NONE | NONE | NONE
LEGEND
FULL = Full read/write access ¦ ADMIN = Administrative access ¦ READ = Read-only ¦ LIMITED = Supervised/restricted ¦ NONE = No access ¦ Own only = Own records only
LIVE USER REGISTER
Full Name | Role | Email | M365 Plan | Start Date | 2FA Active? | Access Level | Status
Maher Farea | CEO / Interim CTO | m.farea@kayanwork.com | Business Standard | Jan 2026 | YES | FULL | ACTIVE
Dev 1 (Mustafa Haney) | Lead Developer | dev1@kayanwork.com | Business Standard | Feb 2026 | PENDING | DEV+ADMIN | ACTIVE
Dev 2 (TBC) | Frontend Developer | dev2@kayanwork.com | Business Basic | Mar 2026 | PENDING | DEV+FRONTEND | ACTIVE
TBD | Finance Lead | finance@kayanwork.com | Business Standard | TBD | — | FINANCE | PLANNED
TBD | HR Lead | hr@kayanwork.com | Business Standard | TBD | — | HR | PLANNED
TBD | Ops Manager | ops@kayanwork.com | Business Basic | TBD | — | OPS | PLANNED
TBD | ICT Ops Intern | intern.ict@kayanwork.com | Business Basic | May 2026 | — | SUPERVISED | RECRUITING
TBD | Frontend Dev Intern | intern.dev@kayanwork.com | Business Basic | May 2026 | — | SUPERVISED | RECRUITING

## 📧 MUSTAFA BRIEF
📧 BRIEF FOR MUSTAFA HANEY (Dev Lead) — From: Maher Farea, CEO ¦ Date: 16 April 2026
This tab is your complete, standalone brief. Everything else in this workbook is context and reference. This is what you need to know, what you need to do, and when. If something is unclear — email m.farea@kayanwork.com. CEO responds within 24 hours.
🎯 WHAT YOU ARE BUILDING
Primary product | Kayan Innovation's complete digital infrastructure: kayanwork.com (bilingual website, 8 pages) + platform.kayanwork.com (managed delivery platform with 11 mandatory modules including escrow gate, SOW builder, client portal, talent portal, RBAC admin). This is the revenue engine for a real operating company launching 01 May 2026.
Secondary product | CauseWay platform (separate entity, shared dev team): Next.js + Directus CMS + PostgreSQL + Digital Ocean. Sprint March 4-17 2026 plan is your reference. CauseWay cost is split 50/50 with Kayan.
Your platform stack (Kayan) | Next.js 14 (TypeScript, App Router, Tailwind, PWA) + NestJS backend + PostgreSQL (Prisma ORM) + Redis + Docker + Nginx + Hetzner CX31 VPS + Cloudflare + GitHub Actions CI/CD + Claude API for AI features
Non-negotiable founding law | NO SOW + NO ESCROW (100% funded) = NO WORK. This rule is hard-coded at the database level. You cannot create exceptions. It is in your contract. Any code that weakens this rule is grounds for immediate termination.
⏰ CRITICAL DEADLINES
01 May 2026 — DAY-1 GO-LIVE | kayanwork.com + platform.kayanwork.com LIVE. All 11 modules functional. QA gates passed. Non-negotiable.
22 April 2026 — Staging deadline | Modules 01-11 functional in staging. Internal end-to-end test: client registers → SOW → escrow → milestone → payout. With CEO.
28 April 2026 — QA deadline | All 4 QA gates must show PASS: Legal survivability; Audit readiness; Arabic RTL on Chrome/Safari/Firefox mobile; Aden resilience (3G load test, 50 concurrent users).
23 April 2026 — YETO API keys | Register free API keys for 8 blocked data sources: ACLED, FAO, ILO, UN Comtrade, IPC, UNCTAD, WHO, UNESCO. Takes 5-10 min each. Unlocks 5,000+ data points. See YETO TODO report.
Pre Day-1 — M365 setup | CEO activates M365. Your account: dev1@kayanwork.com (Business Standard). You set up SharePoint portal Phase 1 + Power Automate first approval flow.
Week of 21 April — GitHub setup | Create Kayan repo under CausewayGrp org. CEO (MaherFSF) must have owner-level access. Set up GitHub Copilot Business for your seat (CausewayGrp billing).
📋 YOUR ACCOUNTABILITY RULES
Weekly report | Every Thursday, 17:00 Aden time. Email to m.farea@kayanwork.com AND Teams #dev-updates. Format: (a) completed; (b) next week; (c) blockers needing CEO decision. No exceptions.
Production deployments | Teams message to CEO before every production push: what you're deploying + rollback plan. CEO must acknowledge. Then deploy.
Payment | EGP 13,500/month. 50% Kayan, 50% CauseWay. Dual approval required (CEO + Finance) via Power Automate before each payment. InstaPay: matrix1912@instapay.
Code | All source code under CausewayGrp GitHub. MaherFSF = owner. No production code outside this org.
AI tools rule | GitHub Copilot Business is the only approved coding AI tool. No client data, no financials, no sensitive data into any AI tool. See KAY-ICT-POL-001.
6-month review | 15 October 2026. Formal review: sprint performance, CTO hire decision, intern conversion, Yeto Phase 2 capacity. All decisions written.
🛍️ READY PRODUCTS — YOUR DELIVERABLE LIST
What are Ready Products | Fixed-scope, fixed-price deliverables clients can commission in one click. No custom SOW required. Routes through escrow gate. 20 products in the catalog. Your job: build the catalog UI on /services and implement the commission flow.
Top 5 to implement first | (1) Website in 14 Days $800; (2) Landing Page $400; (3) Brand Identity Package $500; (4) Arabic-English Translation $25/1K words; (5) Monthly Social Media $300/mo. These are Day-1 revenue.
Commission flow | Client clicks 'Commission This' → lands on intake form → pays 100% upfront via escrow → Kayan receives, assembles team → delivers within stated timeline → escrow releases net of 20% fee → client receives invoice.
Your role | Build the /services Ready Products section on kayanwork.com. Each product card has: name (AR+EN), description, timeline, price, what's included, what's not, and a commission CTA. 20 products in the READY PRODUCTS tab of this workbook.
🌐 WEBSITES — CLIENT COMMISSIONS PIPELINE
Upcoming demand | CEO intelligence: 5+ website commissions expected in the next 2 months (businesses, NGOs, individuals). Kayan must be ready to deliver.
Your capacity rule | No client website project may start if it reduces your Kayan platform delivery availability below 60%. All external projects start after 01 June 2026.
Small sites (< $500) | Use interns + pre-built template (Webflow/WordPress). You review only. Intern-handleable.
Medium sites ($500-$2K) | Use the CauseWay tech stack (Next.js + Directus). You lead. Dev 2 and FE intern support. Use CauseWay Sprint Plan as delivery template.
Large projects (> $2K) | CEO re-strategises. Potential Dev 3 hire. Formal SOW + escrow gate mandatory. Do NOT start without full approval chain.
Egypt freelancer pool | CausewayGrp network in Cairo. For lower-complexity builds to protect your capacity. You do QA only.
📦 INFRASTRUCTURE TO SET UP
Hetzner CX31 VPS | $20/month. Provision: Docker + Docker Compose, Nginx reverse proxy, Let's Encrypt SSL, Cloudflare DNS, GitHub Actions CI/CD. Guide: use the CauseWay sprint plan structure.
Bitwarden self-hosted | Deploy on Hetzner in < 2 hours. Create shared vaults for CEO, Finance, Ops. This eliminates credential sharing via WhatsApp immediately. Free.
GitHub Actions CI/CD | Auto-deploy on merge to main. Health check after each deploy. Tag v1.0.0 for Day-1 release.
Cloudflare | Set up DNS for all subdomains: kayanwork.com, platform., space., academy., admin., volunteers., impact., api., staff., yeto., bid. SSL via Cloudflare universal SSL (free).
❓ WHAT MAHER NEEDS FROM YOU
By 18 April (48h from now) | Reply to this brief with: (1) Sprint S2 plan for 1-14 Apr; (2) Sprint S3 plan for 15-30 Apr; (3) any technical blockers that require CEO decision
By 22 April (staging) | All 11 modules functional in staging. Book a 1-hour review session with CEO.
By 28 April (QA) | All 4 QA gates showing PASS. Screenshot evidence to CEO via Teams.
By 01 May (go-live) | Live. First real user registers. First client intake form submitted.
Every Thursday (ongoing) | Weekly delivery report. No exceptions. This is your primary accountability mechanism.