## 00 · START
KAY-CMP-001 · The 12-Month Campaign Programme — live model
One story across twelve months (Aug 2026 – Jul 2027). Calendar, register, a self-costing budget, sponsorship pipeline, and the give-back engine. Companion to KAY-CMP-001.
HOW THIS WORKBOOK WORKS
• The 12 campaigns run as one story in four acts, colour-coded: Arrival (blue), Proof (green), Mobilise (red), Scale (amber).
• The budget model is self-costing: fill each campaign's six lines and it totals the campaign, offsets sponsorship, and rolls up the year.
• The sponsorship pipeline tracks prospects by tier and stage; the give-back engine tracks community projects, hours, and earned tiers.
• Nothing is invented. Lavender cells are tokens awaiting the F-01 decision session (forks F-11 to F-14).
TAB GUIDE
| 01 · THE YEAR | The twelve-month calendar — every campaign against its months, coloured by act.
| 02 · CAMPAIGN REGISTER | All twelve campaigns and the standing bank, with objective, hero moment, owner and KPIs.
| 03 · BUDGET MODEL | The self-costing model: six lines per campaign, sponsorship offset, annual roll-up.
| 04 · CONTENT ENGINE | The six pillars and the platform plan that carry every campaign.
| 05 · SPONSORSHIP | The five tiers and a prospect pipeline by stage and value exchange.
| 06 · GIVE-BACK ENGINE | The community-project pipeline and the hours-to-tiers-to-points mechanics.
| 07 · KPI DASHBOARD | The programme funnel and the one governing number.

## 01 · THE YEAR
The year — one story in four acts
Each campaign against the month it runs. Colour marks the act. The always-on bank runs beneath all twelve.
| Campaign | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
CMP-01 | We Build It Together
CMP-02 | The Map
CMP-03 | A Place to Build
CMP-04 | Proof, Not Promises
CMP-05 | Build Home From Anywhere
CMP-06 | New Year, New Work
CMP-07 | Ten Nights, Ten Skills
CMP-08 | Eid: Behind Every Success
CMP-09 | She Delivers
CMP-10 | The Sector Series — Digital Delivered
CMP-11 | From Campus to Career
CMP-12 | One Year, Behind Every Success
| ACTS: |  | Arrival |  | Proof |  | Mobilise |  | Scale

## 02 · CAMPAIGN REGISTER
Campaign register
Every campaign as a managed line — objective, the moment that carries it, owner, status, budget envelope, and how it is measured.
| Campaign | Month | Act | Objective | The moment | Owner | Budget | Measured by
CMP-01 | We Build It Together | August 2026 | Arrival | Establish Kayan's name, meaning, and sonic identity across Aden, and convert attention into the first wave of registrations. | The first hundred verified names lighting up on the Founders' Wall as the sonic signature plays. | POS-BRD-LEAD | [[PH-CMP01-BUDGET]] | Reach across channels · Registrations opened in the launch window · Founders' Wall names secured · Founding Partner signed
CMP-02 | The Map | September 2026 | Arrival | Drive verified registrations and establish the map as the public evidence of Yemeni capability. | A governorate lighting up on the map for the first time, with the name and craft of its first verified talent. | POS-TAL-LEAD | [[PH-CMP02-BUDGET]] | Verified registrations completed · Governorates represented on the map · Specialisations covered · Campaign Partner secured
CMP-03 | A Place to Build | October 2026 | Arrival | Establish the Hub as the physical home of the Kayan community and convert visits into memberships and pod formation. | A time-lapse of the Hub filling through the open week, ending on a formed pod at a table. | POS-HUB-EXP | [[PH-CMP03-BUDGET]] | Open-week visitors · Memberships taken · Pods formed on-site · Sponsor for working conditions secured
CMP-04 | Proof, Not Promises | November 2026 | Proof | Generate qualified client briefs into the pipeline and convert first-time clients through low-risk entry services. | The delivery ledger ticking over — a wall of delivered work that speaks for itself. | POS-MD-LEAD | [[PH-CMP04-BUDGET]] | Qualified briefs into the pipeline · First-time clients converted · Quick-return engagements sold · Proof cards published
CMP-05 | Build Home From Anywhere | December 2026 | Proof | Open diaspora demand and sponsorship, and close the year on a credible impact story. | A diaspora founder and their Aden pod meeting over video as the work ships — distance closed by delivered work. | POS-MD-LEAD | [[PH-CMP05-BUDGET]] | Diaspora briefs received · Cohort or project sponsorships secured · Impact report reach · Diaspora registrations (talent abroad)
CMP-06 | New Year, New Work | January 2027 | Proof | Fill the Forge cohort and convert learners into verified talent on a path to paid work. | A Forge graduate from an earlier cohort leading a pod on a real client brief. | POS-FRG-LEAD | [[PH-CMP06-BUDGET]] | Cohort applications and places filled · Learners progressing to verification · Sponsor-funded seats secured · Prior-cohort placement proof
CMP-07 | Ten Nights, Ten Skills | February–March 2027 | Mobilise | Mobilise volunteers, deliver visible community value, secure sponsor funding, and showcase the give-back-for-standing system at scale. | Ten community projects handed over by Eid, beside a wall of volunteers and the card tiers their hours earned. | POS-K4Y-CO | [[PH-CMP07-BUDGET]] | Volunteers mobilised · Verified community hours given · Community projects delivered · Card tiers earned through volunteering · Sponsors secured and funds raised
CMP-08 | Eid: Behind Every Success | March 2027 | Mobilise | Deepen loyalty and community belonging, and convert gratitude into retention and word of mouth. | The highest volunteer card tiers celebrated by name, with the hours and the projects behind them. | POS-K4Y-CO | [[PH-CMP08-BUDGET]] | Volunteers recognised · Community engagement and sentiment · Retention of Ramadan volunteers into ongoing giving
CMP-09 | She Delivers | April 2027 | Mobilise | Increase women's registration, verification and pod participation, and secure sponsorship for women's economic inclusion. | A woman-led pod delivering a significant client project, in their own words. | POS-TAL-LEAD | [[PH-CMP09-BUDGET]] | Women registering and completing verification · Women-led pods placed · Verification-fee sponsorship secured · Women's cohort filled
CMP-10 | The Sector Series — Digital Delivered | May 2027 | Scale | Convert sector-specific demand into briefs while driving verified registration in the same sector. | A verified sector team beside the delivered project that proves the sector works, here. | POS-MD-LEAD | [[PH-CMP10-BUDGET]] | Sector briefs into the pipeline · Sector registrations and verifications · Sector proof cards published · Format documented for reuse
CMP-11 | From Campus to Career | June 2027 | Scale | Convert graduating students into verified talent through university partnerships, and deepen government youth-employment engagement. | A new graduate, weeks after finishing, delivering paid work as part of a verified pod. | POS-FRG-LEAD | [[PH-CMP11-BUDGET]] | University partnerships signed · Graduates registered and verified · Graduates placed into pods · Government engagement advanced
CMP-12 | One Year, Behind Every Success | July 2027 | Scale | Consolidate the year's proof into reputation and momentum, and open the investor and venture conversation. | The Founders' Wall from August, one year on, full — beside the year's numbers. | POS-CEO | [[PH-CMP12-BUDGET]] | Anniversary reach and reputation lift · Founding partners renewed · Investor conversations opened · Annual impact report distributed
STANDING BANK (always-on / tactical)
| Concept | Cadence | What it is | For
BNK-01 | Faces of the Map | Always-on | A rolling weekly spotlight of one verified talent — craft, story, a delivered piece. The human layer beneath the map, running all year. | AUD-TAL, AUD-CLI
BNK-02 | The Delivery Ledger | Always-on | Every completed pod project published as a proof card, continuously. The demand engine's quiet, constant proof. | AUD-CLI
BNK-03 | Met Here | Always-on | Short stories of pods that formed at the Hub and won work — the Hub's promise, proven repeatedly. | AUD-HUB, AUD-TAL
BNK-04 | 48 Hours | Tactical | A recurring quick-return challenge — a brand, a landing page, an annotated set delivered in 48 hours, filmed. Proof of speed for first-time clients. | AUD-CLI
BNK-05 | Give-Back Ticker | Always-on | A live count of community hours given, projects delivered, and card tiers earned — the civic engine visible year-round, not only in Ramadan. | AUD-VOL, AUD-SPO
BNK-06 | Ask a Verified Expert | Tactical | A verified talent answers a real question publicly — useful content that proves expertise and feeds registration interest. | AUD-TAL, AUD-CLI
BNK-07 | Sponsor Spotlight | Always-on | A short, dignified feature of what a sponsor's funding built — the reported line from money to outcome, made shareable. | AUD-SPO
BNK-08 | The Diaspora Desk | Always-on | A standing channel and story stream for diaspora clients and sponsors — 'build home from anywhere', continuous. | AUD-DIA

## 03 · BUDGET MODEL
The self-costing budget model
Fill each campaign's six lines (yellow). The model totals each campaign, subtracts sponsorship raised, and rolls up the year. Nothing is set — lines are yours.
| Campaign | Creative production | Media & boost | Event & activation | Print & physical | Creator & talent fees | Sponsorship servicing | Gross | Sponsorship raised | Net
CMP-01 | We Build It Together
CMP-02 | The Map
CMP-03 | A Place to Build
CMP-04 | Proof, Not Promises
CMP-05 | Build Home From Anywhere
CMP-06 | New Year, New Work
CMP-07 | Ten Nights, Ten Skills
CMP-08 | Eid: Behind Every Success
CMP-09 | She Delivers
CMP-10 | The Sector Series — Digital Delivered
CMP-11 | From Campus to Career
CMP-12 | One Year, Behind Every Success
Σ | PROGRAMME — ANNUAL
All totals read 0 until the lines are filled — by design. When F-11 and F-12 resolve the budget lines and sponsorship values, the whole year costs itself: gross cost, sponsorship offset, and net, per campaign and in total.

## 04 · CONTENT ENGINE
The content engine
Six pillars keep a year of content coherent; the platforms carry it where the audience is.
THE SIX PILLARS
Pillar | What it carries | Why it earns its place
Proof | Delivered work, the ledger, client outcomes. | Every proof answers a buyer's fear.
Faces | Verified talent, pods, the people on the map. | People trust people, not platforms.
Place | The Hub, the café, pods forming, the safe space. | The home makes the promise tangible.
Give-back | Volunteers, community projects, cards and points earned. | Standing earned by giving is Kayan's civic heart.
Learn | Forge cohorts, the learn–verify–work path, graduates. | The bridge from skill to income.
Model | How Kayan works — escrow, verification, pods — explained plainly. | Clarity converts; confusion loses.
THE PLATFORMS
Platform | Its role | What it carries
Facebook | Broad Aden reach; community and local news. | Reach, community, event mobilisation.
Instagram | Story and craft; talent faces and Hub life. | Brand, talent spotlights, culture.
TikTok | Short, human, behind-the-scenes; youth reach. | Youth talent acquisition, Hub life, speed proofs.
WhatsApp | The direct channel; registration and coordination. | Registration link, volunteer coordination, client and diaspora relationships.
LinkedIn | The professional and institutional audience. | Clients, INGOs, government, donors, investors.
X | Timely, public-facing statements and threads. | Announcements, sector and policy conversations.
THE RULES
• Every campaign ships with a content kit — the hero asset, the cut-downs per platform, and the always-on tie.
• The sonic signature opens brand moments; the promise closes them.
• WhatsApp carries the registration link as the single, low-friction call to action across campaigns.
• Owned and earned content leads; paid boost amplifies the proven, it does not replace the story.
• Do no harm governs every post: no conflict framing, no faction, dignity in every face shown, consent before naming.

## 05 · SPONSORSHIP
Sponsorship — tiers and pipeline
An association offered with a value exchange and a reported outcome — never a generic ask. Track prospects by tier and stage.
THE TIERS
Tier | What it is | What the sponsor receives | Contribution
Founding Partner | The institution named as a builder of Kayan from day one. | Name and mark on the Founders' Wall; first association with the system; founding-year impact report; renewal at the anniversary. | [[PH-SPON-FOUND]]
Campaign Partner | A partner attached to a single campaign. | Association with a specific campaign and its outcome; a reported line from support to result. | [[PH-SPON-CAMP]]
Civic Partner | A government body or local authority endorsing a youth-employment or community effort. | Association with a non-partisan youth and community initiative; a planning asset (the map, the outcomes). | Non-financial or [[PH-SPON-CIVIC]]
Cohort Sponsor | A funder of a Forge cohort or a talent-verification cohort. | A named cohort; graduates who reach real work; a reported employment outcome. | [[PH-SPON-COHORT]]
Community Project Sponsor | A funder of a single community give-back project. | A named community project delivered in their name; a clear line from giving to community outcome. | [[PH-SPON-PROJECT]]
PROSPECT PIPELINE (template — add prospects as position-coded or organisation names)
Prospect | Tier | Campaign / cohort | Stage | Value exchange agreed | Owner | Status
STAGES: Identify → Approach → Agree → Service → Report
THE GOVERNMENT MODEL
• Government and local-authority engagement is framed only on youth, skills, employment, and community outcomes.
• The verified talent map and the campaigns' placement and community outcomes are offered as genuine planning assets.
• No engagement aligns Kayan with any faction or takes any position on the conflict. Do no harm is the governing test.
• Local authorities nominate community beneficiaries and co-brand civic campaigns; they do not direct Kayan's independence.

## 06 · GIVE-BACK ENGINE
The give-back engine — volunteers, cards, points
Give a verified skill to the community; earn standing for it. Standing, never money. Peaks in Ramadan; runs all year.
HOW IT WORKS
Step | What happens | Owner
A community need is scoped | A local authority or community institution nominates a real need — a school's site, a clinic's system, an NGO's data. | POS-K4Y-CO
A volunteer pod is formed | Verified talent volunteers; a pod is assembled to deliver, under supervision, exactly as a paid pod would. | POS-TAL-ASM
Hours are given and verified | Volunteer hours are logged against the assignment and confirmed by a supervisor — never self-declared. | POS-K4Y-CO
Standing is earned | Verified hours convert to Kayan Card tiers and points — recognition and access, never money, work, or a purchased tier. | System
The outcome is delivered and named | The community project is handed over; the sponsor who funded it and the volunteers who built it are named, with consent. | POS-K4Y-CO
COMMUNITY-PROJECT PIPELINE (template)
Project | Beneficiary (nominated) | Sponsor | Volunteer pod | Hours given | Tier earned | Status
THE RULES
• Volunteer hours are never billed to a client and never enter the payout pool. The two ledgers never touch.
• Points and card tiers earned by volunteering unlock standing, recognition and access — never money, never paid work, never a tier that must otherwise be verified.
• Hours count only against a real, supervised assignment with sign-off. Manufactured hours earn nothing, because nothing they earn has a price.
• A sponsor may fund a community project; a sponsor may never buy a volunteer's standing or a card tier.
• Beneficiaries are chosen on community need and do-no-harm, nominated by local authorities, never on politics.
The Kayan Card recognises standing in metal bands — the same credential the talent system issues. Volunteer hours are one of the ways a person earns and raises a card, alongside verified work. The card proves standing to the outside world; it never substitutes for the verification a paid engagement requires.

## 07 · KPI DASHBOARD
Programme dashboard
What the year is moving, and the one number it is finally judged on.
WHAT THE YEAR MOVES
Measure | What it counts | What it tells us | Target
Reach & reputation | Total qualified reach; sentiment; share of voice in Aden. | Awareness that the year is building.
Talent supply | Registrations; completed verifications; governorates and specialisations on the map. | The map filling with credible, verified talent.
Client demand | Qualified briefs; first-time clients; quick-return engagements; briefs won. | Demand converting into funded work.
Civic mobilisation | Volunteers; verified community hours; community projects delivered; card tiers earned by giving. | The give-back engine turning.
Sponsorship | Partners secured by tier; funds raised; sponsorship offset against programme cost. | The programme funding itself.
Learning | Cohort places filled; learners progressing to verification and to pods. | The learn–verify–work bridge carrying.
The governing number | Share of the verified registry ever placed. | The one number the whole institution serves. | [[PH-PLACED-TARGET]]
THE GOVERNING NUMBER
Share of the verified registry ever placed
Reach · Registrations · Verified talent · Briefs won · Volunteers · Hours given · Community projects · Sponsors raised — all serve this one.