## 00 HOW TO USE
ROLLING WORK PLAN — POSITIONS, MILESTONES, WORKFLOW, RISKS
خطة العمل المتدحرجة — المناصب والمحطّات وسير العمل والمخاطر
WHAT THIS IS · ما هذا النظام
The Rolling Work Plan is the one document that ties every position, every deliverable, every milestone, every resource, every risk, and every mitigation to where we are going. It is updated continuously: as a milestone is hit, the row turns green; as a new constraint appears, a mitigation is added. The 'ROLLING MASTER' tab is the single comprehensive view. Open it. Filter by Position, Phase, or Priority. |  |  | خطّةُ العمل المتدحرجة هي الوثيقةُ الواحدة التي تربط كلَّ منصبٍ وكلَّ مخرَجٍ وكلَّ محطّةٍ وكلَّ موردٍ وكلَّ خطرٍ وكلَّ معالجةٍ بحيثُ نتّجه. تُحدَّث باستمرار: عند بلوغ محطة، يخضرّ السطر؛ وعند ظهور قيدٍ جديد، تُضاف معالجة. تبويبُ «ROLLING MASTER» هو العرضُ الشامل الواحد. افتحه. وَصَفِّ حسب المنصب أو المرحلة أو الأولوية.
WHERE WE ARE GOING · حيثُ نتّجه
Year 1 | Stand up the institution. Launch soft on 30 June 2026. Cross break-even on Hub. Sign first two INGO contracts. Issue first 50 Kayan Cards. Ship first 10 Managed Delivery projects. |  | السنة الأولى: تأسيس المؤسّسة. إطلاقٌ ناعم 30 يونيو. تجاوز نقطة التعادل في المساحة. توقيع أوّل عقدَين مع منظّمات دولية. إصدار أوّل 50 بطاقة كيان. تسليم أوّل 10 مشاريع توصيل.
Year 2 | Forge net positive. Kayan for Yemen mobilised in three governorates. Launch the Series A. Establish ADGM/DIFC holdco for international investors. |  | السنة الثانية: فورج إلى ربحيةٍ صافية. كيان لليمن في ثلاث محافظات. جولة Series A. تأسيس شركةٍ قابضة في ADGM/DIFC.
Year 3 | Project Memory Flywheel mature. Bank co-brand card live. Recognised as the talent infrastructure of Yemen — a category, not a vendor. |  | السنة الثالثة: نضج دولاب ذاكرة المشاريع. بطاقةُ التعاون مع بنكٍ تَنطلق. الاعترافُ بكيان بنيةً تحتيةً للكفاءات اليمنية — فئةً لا مورّدًا.
Five-year | A network in every Yemeni governorate, a verified talent registry that international clients use by default, a defensible data moat, a self-sustaining institution. |  | الخطّةُ الخمسية: شبكةٌ في كلِّ محافظة، سجلٌّ موثَّقٌ يستخدمه العملاء الدوليون افتراضيًّا، خندقٌ دفاعيٌّ من البيانات، مؤسّسةٌ ذاتيةُ الاستدامة.
↦ Open the ROLLING MASTER plan — one comprehensive view

## 01 ROLLING MASTER
ROLLING MASTER — every position, every deliverable, every milestone
العرض الشامل — كلُّ منصبٍ وكلُّ مخرَجٍ وكلُّ محطّة
# # | PHASE المرحلة | POSITION المنصب | DELIVERABLE / TASK المخرج/المهمّة | MILESTONE (output) المحطّة | WHEN المتى | HOW (mechanic / workflow) الكيفية | RESOURCES الموارد | KPI / DONE-WHEN المؤشّر/متى انتهى | RISK المخاطر | MITIGATION المعالجة | DEPENDENCIES الاعتماد | PRIORITY الأولوية | STATUS الحالة
1 | Pre-launch | CEO (Maher) | Wet-sign Articles of Association with counsel | AoA filed at Commercial Register |  | Notarisation in Aden; counsel files; ministry confirmation | Counsel ($500/yr retainer); CEO time | Commercial Register cert in hand | Filing delay | Weekly counsel + backup firm + pre-built docs | Counsel retained | CRITICAL | In progress
2 | Pre-launch | CEO (Maher) | Resolve Tariq $12K uncalled capital | Either $12K called or quota agreement amended |  | CEO + Tariq meeting; counsel option memo; signed resolution | Tariq + Counsel + CEO time | Resolution recorded; AoA truthful on capital | Disputed; pre-launch delay | Frame as procedural; offer both options openly | AoA filing | CRITICAL | Open
3 | Pre-launch | CEO (Maher) | Open Tadamon + Aden Bank operating + escrow sub-accounts | Both accounts live; signatories registered |  | Tadamon visit; Aden Bank escrow sub-account setup; dual-approval signatories | CEO + Tariq | Bank letters in hand | Account-opening friction | Use existing CEO relationships; pre-prepare KYC | AoA | CRITICAL | Open
4 | Launch month | CEO (Maher) | Soft-launch event 30 June 2026 | Public soft-open; first cohort welcomed |  | Invite partners (UNDP/GIZ/ILO/UN Women local) + 50 talent + press | Hub fit-out · Brand kit · Catering | ≥30 attendees; press coverage | Low turnout | Confirm 50 RSVPs 2 wks ahead; partner co-host | Hub ready · Brand assets | CRITICAL | Open
5 | 30-day | CEO (Maher) | First INGO scoping meetings | ≥3 INGO meetings held |  | Outreach via Aden offices (UNDP SIERY, GIZ, ILO ERRY) | Ali (govt relations); pitch deck | Meetings logged in CRM | No response | Partner-referral intros; Ali persistence | Soft-launch done | HIGH | Open
6 | 90-day | CEO (Maher) | First INGO contract signed | ≥1 contract signed; first donor cohort or pilot |  | Convert scoping meeting → proposal → contract | Counsel; CEO time | Contract in hand; first invoice | Slow procurement | Start with smaller scope; build trust | INGO meetings | CRITICAL | Open
7 | Q2 expansion | CEO (Maher) | WATHBA accelerator application | Application submitted |  | Pitch + financials + pilot evidence | Brand Lead + Finance | Acknowledgement | Application missed | Set calendar reminder; submit early | Year-1 traction | HIGH | Open
8 | Year-1 | CEO (Maher) | ADGM/DIFC holdco scoping | Decision memo; setup if chosen |  | Comparative memo with Counsel; investor input | $5-8K setup; counsel | Decision recorded; setup if green | High cost vs benefit | Defer to traction; revisit at Series A prep | Series A intent | MEDIUM | Open
9 | Pre-launch | Finance Lead (Tariq) | COA + opening balances in FIN-SYS | All 53 accounts seeded; opening balances locked |  | Use KAY-FIN-SYS-001 v1; reconcile vs FIN-MASTER | Finance Lead time | Trial balance balances; zero errors | Setup errors | Two-pass review with CEO | FIN-SYS workbook | HIGH | In progress
10 | Pre-launch | Finance Lead (Tariq) | Sign-off on Accountability Charter v2 (corrected cap table) | Counter-signed v2 |  | Review v2; meet CEO + counsel; sign | Tariq time | v2 in legal file | Concerns over $12K resolution | Resolve $12K item first | $12K item | CRITICAL | Open
11 | Launch month | Finance Lead (Tariq) | First monthly close (June) | P&L + balance sheet + cash; reconciled to bank |  | Run KAY-FIN-MASTER process; reconcile Tadamon + Aden Bank | FIN-MASTER workbook; bank statements | Close by 5th of next month | Mismatches | Daily journal hygiene; review with CEO | Banks open | HIGH | Open
12 | 30-day | Finance Lead (Tariq) | Payroll first run + SI registration | All 4 active staff paid; SI numbers issued |  | Tadamon transfer; SI office visit (Ali support) | HR data; bank | First payslips issued | SI office delays | Submit early; Ali follow-up | Hires onboarded | HIGH | Open
13 | 90-day | Finance Lead (Tariq) | First quarterly P&L vs plan | Q3 close with variance commentary |  | Compare actuals to KAY-FIN-MOD-001 forecast | Closed books | Variance memo to partners | Negative variance | Frame honestly; adjust forecast | Monthly closes | HIGH | Open
14 | Year-1 | Finance Lead (Tariq) | Year-1 audit-ready file | Books audit-ready; audit log integrity |  | Annual close; reconcile audit log; engage external audit | Auditor; closed books | Audit opinion | Audit findings | Strong monthly hygiene | Year of closes | HIGH | Open
15 | Pre-launch | Mohamed (Partner) | Acknowledge non-operating role + COI controls | Signed acknowledgement under COI Policy |  | Sign Accountability Charter v2 + COI disclosure form | Charter; COI form | Signatures filed | Misunderstanding of role | Clear writing in Charter; CEO conversation | Charter v2 | CRITICAL | Open
16 | Launch month | Mohamed (Partner) | Introductions to Forge partners (no operational authority) | ≥3 partner intros made |  | Network outreach to universities, training orgs; CEO leads | CEO + Mohamed time | Intros documented | Crossing into operations | Stay within intro-only role; CEO leads conversations | Charter ack | HIGH | Open
17 | Year-1 | Mohamed (Partner) | 12-month cliff vesting check | Sweat-equity portion vests |  | HR records continuous engagement | Charter rules | Vesting recorded | Premature claim | Clear written rules in Charter | Continued engagement | MEDIUM | Open
18 | Pre-launch | Ali (Govt Relations) | Commercial Register filings + tax registration | Tax card + commercial register cert |  | Visit ministry offices; pay fees; collect certificates | Counsel + Ali time | Cert in hand | Filing delays | Pre-built docs; weekly checks | AoA filed | CRITICAL | Open
19 | Launch month | Ali (Govt Relations) | Social Insurance registration | SI numbers for 4 active staff |  | SI office submission; payroll deduction setup | HR data; SI office | SI numbers issued | Documentation gaps | Pre-check requirements | Tax registration | HIGH | Open
20 | Q2 expansion | Ali (Govt Relations) | CSR partnerships with local banks | ≥1 CSR meeting |  | Alkuraimi / Yemen Mobile / SabaFon outreach | Ali network | Meeting logged | No response | Multiple touches; CEO escalation | Soft-launch | MEDIUM | Open
21 | Pre-launch | OFO (Operations & Finance Officer) | Hire OFO | Offer signed |  | YemenHR vacancy live; shortlist; interview | Vacancy pack; CEO + Tariq interview | OFO joins | Talent shortage | Compelling offer + Kayan story | Cash for first salary | HIGH | Open
22 | Launch month | OFO | Run daily ops: bookings, invoices, suppliers | All daily ops handled |  | Use Forms workbook + FIN-SYS | OFO time | Zero blocked days | OFO ramp-up | Strong onboarding week 1 | OFO hired | HIGH | Open
23 | 30-day | OFO | Own the Compliance Calendar | All July deadlines met |  | Track via Governance OS calendar tab | Calendar; reminders | 100% on-time | Misses | Weekly calendar review w/ CEO | OFO familiar | HIGH | Open
24 | Pre-launch | Brand Lead (to hire) | Hire Brand Lead | Offer signed |  | YemenHR vacancy; portfolio review | Vacancy pack | Brand Lead joins | Talent shortage | Compelling brief; Lubna referrals | Cash | HIGH | Open
25 | Launch month | Brand Lead | Launch comms plan executed | Press release + social + partner posts |  | Use brand kit; bilingual cadence | Brand kit; comms calendar | Coverage measured | Low pickup | Pre-seed coverage with friendly journalists | Brand Lead hired | HIGH | Open
26 | 30-day | Brand Lead | First 30 social posts published | 30 posts live; engagement tracked |  | Content calendar (Cairo Arabic + English) | Brand kit | Engagement metrics | Slow start | Adjust cadence weekly | Brand Lead familiar | HIGH | Open
27 | 90-day | Brand Lead | First case study published | 1 case study, bilingual |  | Pick first delivered project; write+publish | Project data | Case study live | No project to feature | Use pilot work | First project done | HIGH | Open
28 | Pre-launch | Hub Lead | Hub physical fit-out + soft-open dry-run | Hub passes walk-through |  | Furniture; Starlink; reception; café fit-out | Capex budget | Walk-through approved | Cost overruns | Phased fit-out | Cash | HIGH | Open
29 | Launch month | Hub Lead | First 5 members onboarded | 5 KC-H issued |  | Use F-EXT-04 form; verification | Forms workbook | 5 members active | Slow signups | Personal outreach; founders bring in network | Soft-open | HIGH | Open
30 | 30-day | Hub Lead | Female-only day Wednesday live | First Wed female day held |  | See Forms WB 15 COMMUNITY PROGRAMMING | Female guard or reception; programming | ≥5 women attendees | Mixed reception | Survey women members first | Women members signed up | HIGH | Open
31 | 60-day | Hub Lead | Recommendations Board live (digital + physical) | Board live; first ideas in |  | SharePoint list + corkboard at Hub | SharePoint setup; corkboard | ≥10 ideas in first month | No engagement | Seed it with 5 starter ideas | Hub live | HIGH | Open
32 | 90-day | Hub Lead | First member-led event | 1 member-led event held |  | Process via F-INT-11 Event Proposal | Up to $50 Kayan support | Event held + feedback | No proposals | Active asking at member meetups | Active members | MEDIUM | Open
33 | Year-1 | Hub Lead | Break-even 28+ paying members | Hub financially self-sustaining |  | Conversion funnel from day-pass → flex → dedicated | Pricing tiers; outreach | Net contribution positive | Breakeven missed | Push community day-pass; promote tier upgrades | Strong community | HIGH | Open
34 | Pre-launch | Café Lead | Café fit-out + menu lock + suppliers | Café passes opening walk-through |  | Lock 12 SKU menu; 3 suppliers; staff training | Café capex | Health-safety pass | Supply chain issues | Multiple suppliers; menu flexibility | Hub fit-out | HIGH | Open
35 | Launch month | Café Lead | Café operational from Day 1 | Café open 06:00 daily |  | SOPs from KAY-OPS-CAF | Barista; supplies | Open and serving | Staffing | Hire 1.5 baristas; co-cover | Café ready | HIGH | Open
36 | 30-day | Café Lead | COGS ≤35% locked | Margin holds |  | Daily Z-report; weekly waste review | POS data | COGS in band | Waste high | Tight portion control; staff training | Café open | MEDIUM | Recurring
37 | Year-1 | Café Lead | Café as community anchor (not profit centre) | ~$1K/mo mature revenue, near break-even after contribution costs |  | Cost rationalisation per KAY-FIN-RAT-001 | Member traffic | Anchors footfall | Pressure to over-engineer | Honest positioning: community first | Community programming | MEDIUM | Recurring
38 | 30-day | Forge Lead — Mohamed Faisal Saeed Farea | First donor cohort delivered | 1 cohort completed, 70%+ employment in 90d |  | See Forge OS train→assess→verify→place | Donor funding; instructor pool | Outcomes reported | No donor contract | Use INGO scoping output; smaller pilot | INGO contract | HIGH | Open
39 | 90-day | Forge Lead | First corporate cohort | 1 paid corporate cohort |  | Tailored design; corporate sales | Corporate sales pipeline | Paid invoice | No corporate buyer | Outreach via Mohamed network | Reputation | MEDIUM | Open
40 | Q2 expansion | Forge Lead | Free entry routes live | ≥3 free routes running (1-day trainings, scholarship, sponsor-a-seat) |  | Partner-funded design | Partner co-funding | Inclusion KPI ≥50% women/IDP | Funding gap | Partner-by-partner agreements | Partners | MEDIUM | Open
41 | Pre-launch | Verification Lead (interim CEO) | First 50 talent profiles registered | 50 talent in registry |  | Outreach to existing network + soft-launch event | Forms; Hub for verification | 50 KC-T issued | Slow signups | Pre-seed via Lubna network + LinkedIn | Forms live | CRITICAL | In progress
42 | Launch month | Verification Lead | Verification SLA 5 working days | ≥90% of new talent verified within 5 days |  | Use auto-scheduler; in-person + online | Verifier time | SLA met | Volume spike | Batch verification days | Auto-scheduler | HIGH | Open
43 | 90-day | Verification Lead | First T3 (Pod-ready) talent | ≥5 T3 talent |  | Successful pod placements | Project pipeline | T3 in registry | No projects | Sales drives pod work | First projects | HIGH | Open
44 | Year-1 | Verification Lead | First T4 (Trusted lead) | ≥1 T4 |  | Sustained excellence + lead role | T3 base | T4 conferred | Bar too high | Calibrate criteria honestly | Long-tenure T3s | MEDIUM | Open
45 | Pre-launch | Mustafa (Lead Dev) | Hetzner + DNS + SSL provisioned | kayanwork.com + card.kayanwork.com live HTTPS |  | Hetzner CX31; Cloudflare DNS; LetsEncrypt | Hetzner ~$30/mo | Sites resolve | Provider issues | Backup provider noted | ADR-001 | CRITICAL | In progress
46 | Pre-launch | Mustafa | NestJS backend skeleton + JWT + Prisma | API live; JWT issues tokens |  | From 137-file definitive package | Mustafa time | Endpoints respond | Build delays | Prioritise auth + DB only first | Hetzner up | CRITICAL | In progress
47 | Pre-launch | Mustafa | Escrow state machine + 7 Constitutional Rules | DB triggers enforce C1-C7 |  | SOW + Escrow tables; state transitions; dual-approval | Mustafa + Finance Lead | Test transactions pass | Logic bugs | Pair-review with Finance Lead | Schema | CRITICAL | Open
48 | Launch month | Mustafa | card.kayanwork.com public verification page | Public page resolves a valid card ID |  | QR-checkable; pulls from registry | Mustafa | First 50 cards verifiable | Verification gaps | Manual fallback | Cards issued | CRITICAL | Open
49 | 30-day | Mustafa | volunteers.kayanwork.com live | K4Y sign-up flow live |  | Sub-domain; volunteer form; KC-V issuance | Mustafa | Form receives submissions | Build delay | De-scope to v1 | API ready | HIGH | Open
50 | 90-day | Mustafa | Admin panel v1 + reports | Admin panel live for ops |  | Build per Forms WB §07 | Mustafa | CEO can run reports | Scope creep | Strict v1 scope | Auth + DB | HIGH | Open
51 | Year-1 | Mustafa | Project Memory Flywheel data layer | Structured data on every completed project |  | Schema extensions + analytics views | Mustafa | Data captured per project | Schema thrash | Lock schema early | Several projects done | HIGH | Open
52 | Pre-launch | Guards (×3) | Hire 3 guards, contract + onboarding | All 3 signed, trained on SOPs |  | Local recruitment; SOP training | Hiring budget | All onboarded | Talent supply | Multiple candidates; community references | HR Policy | HIGH | Open
53 | Launch month | Guards (×3) | 24/7 cover from 30 June | Three shifts running (06-14, 14-22, 22-06) |  | Per KAY-OPS-FORMS-DB-001 §14 | Three guards | Cover unbroken | Sickness gaps | Cross-cover plan; emergency standby | Guards hired | CRITICAL | Open
54 | 30-day | Guards (×3) | F-INT-01 Daily Log submitted every shift | 100% log submission |  | Mobile form at end of shift | Mobile tablet | 100% submission | Forgetting | Reminder at handover | Form live | HIGH | Recurring
55 | Year-1 | Guards (×3) | Zero serious safety incidents | No High/Critical incidents |  | Active patrols; CCTV; escalation matrix | Equipment | Incident dashboard clean | Unforeseen events | Quick escalation; insurance | Vigilance | HIGH | Recurring
56 | Launch month | Volunteers (K4Y) | First 20 volunteers signed up | 20 KC-V issued |  | Outreach to universities + community | Brand outreach | 20 KC-V active | Slow signups | Pre-seed via community network | K4Y form live | HIGH | Open
57 | 90-day | Volunteers (K4Y) | First fast-track conversions to KC-T | ≥3 volunteers at 40hr threshold convert |  | See Forms WB Workflow 2 | Hours tracking | ≥3 fast-tracks | Low engagement | Active events; visible recognition | Active K4Y community | MEDIUM | Open
58 | Year-1 | Volunteers (K4Y) | Mobilise across 3 governorates | K4Y active in Aden + 2 more |  | Open chapters via partner orgs | Partner support | 3 active chapters | Logistics | Start in adjacent governorates | Aden operation | MEDIUM | Open
59 | Pre-launch | Counsel | Lock weekly retainer | Retainer signed; counsel on board |  | Identify firm; counter-sign agreement | $500/yr budget | Counsel on retainer | Wrong fit | Two-firm shortlist | Cash | HIGH | Open
60 | Pre-launch | Counsel | Draft client MSA template | MSA in repo |  | Standard SOW + escrow + IP + dispute | Counsel time | Template approved | Slow drafting | Use existing template + adapt | Counsel retained | HIGH | Open
61 | Year-1 | Counsel | Quarterly governance review | 4× compliance + governance reviews |  | Charter + policy register + risk review | Counsel time | Reviews documented | Skipped reviews | Calendar block | Counsel active | MEDIUM | Recurring
TOTAL: 61 tracked work items across 7 phases · 14 positions/roles · revisited every session · this is the one document that answers 'who does what, when, how, with what resources, against what risk'