## README
Kayan Yemen — Execution Tracker (Year 1)
How to use
1) Do NOT edit locked cells (grey). Only edit white cells.
2) Weekly: update Status, % Complete, Notes, and Risks. Log decisions in 'Decisions'.
3) Contributions: log all cash/time/in-kind in 'Contributions'. Equity vesting updates automatically.
4) Comments/edits: add your name + date + note in 'Change Log'.
5) Any spend > $1,000 must be recorded in 'Decisions' with Steering Committee reference.
6) Use 'GANTT' to see overlaps; use 'Dashboard' to see where you are slipping.
Tab guide
Tab | Purpose
Dashboard | High-level KPIs, burn, and weekly progress summary.
GANTT | 52-week plan with overlaps; update dates/status here.
RACI | Accountability matrix by workstream.
Hiring | Roles, timing, contract type, and onboarding checklist.
Partners & Donors | Pipeline tracker (MoUs, grant calls, due diligence).
Employers | Employer pipeline + roles + shortlists + placements.
Verification Ops | Throughput, backlog, SLA tracking, QA audit log.
Budget Control | Monthly budget vs actual (manual entry) + links to Annex D.
Equity & Vesting | Locked unit allocations + vesting schedule + contribution linkage.
Contributions | Log cash/time/in-kind with evidence.
Risks | Risk register with owners and mitigations.
Decisions | Decision log (who/when/why) — required for governance.
Change Log | Edits/comments log for accountability.

## Dashboard
Dashboard — Kayan Yemen (Year 1)
Core KPIs (update weekly)
KPI | Value | Source
Registrations (total) |  | (link to Verification Ops / Employers / Budget Control)
Tier 1 approved (total) |  | (link to Verification Ops / Employers / Budget Control)
Tier 2 approved (total) |  | (link to Verification Ops / Employers / Budget Control)
Women share (%) |  | (link to Verification Ops / Employers / Budget Control)
Employer partners (active) |  | (link to Verification Ops / Employers / Budget Control)
Roles received (monthly) |  | (link to Verification Ops / Employers / Budget Control)
Shortlists delivered (monthly) |  | (link to Verification Ops / Employers / Budget Control)
Placements (total) |  | (link to Verification Ops / Employers / Budget Control)
Month burn (USD) |  | (link to Verification Ops / Employers / Budget Control)
Runway (months) |  | (link to Verification Ops / Employers / Budget Control)
Weekly summary (auto from GANTT if desired)
Week | Top priorities | Blockers | Owner

## GANTT
52-Week Gantt — Kayan Yemen (Aden-first)
 | time axis 2026-02-03 to 2027-01-26
Workstream | Task | Owner | Start | End | Status | % Complete | Dependencies | Notes | W1 03-Feb | W2 10-Feb | W3 17-Feb | W4 24-Feb | W5 03-Mar | W6 10-Mar | W7 17-Mar | W8 24-Mar | W9 31-Mar | W10 07-Apr | W11 14-Apr | W12 21-Apr | W13 28-Apr | W14 05-May | W15 12-May | W16 19-May | W17 26-May | W18 02-Jun | W19 09-Jun | W20 16-Jun | W21 23-Jun | W22 30-Jun | W23 07-Jul | W24 14-Jul | W25 21-Jul | W26 28-Jul | W27 04-Aug | W28 11-Aug | W29 18-Aug | W30 25-Aug | W31 01-Sep | W32 08-Sep | W33 15-Sep | W34 22-Sep | W35 29-Sep | W36 06-Oct | W37 13-Oct | W38 20-Oct | W39 27-Oct | W40 03-Nov | W41 10-Nov | W42 17-Nov | W43 24-Nov | W44 01-Dec | W45 08-Dec | W46 15-Dec | W47 22-Dec | W48 29-Dec | W49 05-Jan | W50 12-Jan | W51 19-Jan | W52 26-Jan
Governance | Sign Kayan Unit Agreement under Greenists (founders + investor) | Maher | 2026-02-03 | 2026-02-17 | Not started | 0%
Finance | Open ring-fenced ledger + cash controls + procurement log | Finance/Admin | 2026-02-03 | 2026-02-24 | Not started | 0%
Product/Tech | Contract MVP build ($5,009) + deploy forms | Tech Dev | 2026-02-03 | 2026-03-05 | Not started | 0%
Brand/Media | Brand kit + landing page + launch materials | Alhakimi | 2026-02-03 | 2026-02-13 | Not started | 0%
Outreach | Build WhatsApp recruitment network + university contacts | Faisal | 2026-02-03 | 2026-03-05 | Not started | 0%
Verification Ops | Train verifiers + run Tier 1–2 workflow pilot (20 cases) | Ops/Verification | 2026-02-13 | 2026-03-10 | Not started | 0%
Launch | Public registration launch (Aden-first) | Maher | 2026-02-18 | 2026-02-24 | Not started | 0%
Verification Days | Verification Day #1 (Aden) | Faisal | 2026-02-28 | 2026-02-28 | Not started | 0%
Employers | Employer outreach sprint (20 orgs) + first role intake | Abdulkawi | 2026-02-23 | 2026-03-25 | Not started | 0%
Matching | Deliver first 3 shortlists | Maher | 2026-03-10 | 2026-04-14 | Not started | 0%
Women-first | Women-only onboarding session + cohort plan | Faisal | 2026-03-05 | 2026-04-04 | Not started | 0%
Donors | Donor pack + 3 concept notes submitted | Maher | 2026-03-05 | 2026-05-04 | Not started | 0%
Verification Days | Verification Day #2 (Aden) | Faisal | 2026-04-04 | 2026-04-04 | Not started | 0%
Quality | Monthly audit cycle starts (10% Tier 2) | Ops/Verification | 2026-04-04 | 2027-02-03 | Not started | 0%
Revenue | Employer packages go paid (Standard package) | Maher | 2026-05-04 | 2026-06-03 | Not started | 0%
Scale | Add 1 new specialization (IT/Web or Finance) after proof | Steering | 2026-08-02 | 2026-09-01 | Not started | 0%

## RACI
RACI — Accountability Matrix
Workstream | Key outputs | R | A | C | I
Verification | Tier 1–2 throughput + QA | Ops/Verification | Maher | Faisal, Tech Dev | Steering
Training Partnerships | MoUs + cohorts | Faisal | Maher | Alhakimi | Steering
Marketing/Media | Campaigns + PR | Alhakimi | Maher | Abdulkawi | Steering
Employer Revenue | Shortlists + paid packages | Maher/Abdulkawi | Maher | Ops/Verification | Steering
Finance & Controls | Ring-fenced accounts | Finance/Admin | Maher | Greenists finance | Steering
Tech/Product | MVP + maintenance | Tech Dev | Maher | Ops/Verification | Steering

## Hiring
Hiring Plan — Year 1
Role | Type | Start month | Monthly cost (USD) | Who recruits | Notes
Ops/Verification Manager | Full-time | Month 1 | 700 | Maher | Core quality gate
Finance/Admin | Part-time | Month 1 | 350 | Maher | Ring-fenced accounts
Verification Officer | Part-time | Month 2 | 400 | Ops Manager | Scale throughput
CRM/Data assistant | Part-time | Month 2 | 300 | Ops Manager | Clean CRM + reporting
Tech retainer | Service | Month 2 | 200 | Maher | Maintenance after MVP

## Partners & Donors
Partners & Donors Pipeline
Partner | Type | Value | Due diligence | Agreement | Status | Owner | Next action | Due date | Notes
Yemen Foundation for Training & Development | Training partner | Training delivery + trainer roster | Verify legal registration + trainer roster + references | MoU (Annex E) | Target | Faisal | Schedule due diligence call/visit
Sandbox Aden | Incubator/venue | Verification day venue + recruitment | MoU review | MoU | Target | Maher | Request meeting
SMEPS / BRAVE Women | Donor/implementer | Women cohort underwriting + SME links | Partner fit check | Sponsorship addendum | Target | Maher | Send donor pack
EFE-Yemen | Training/placement | Employer links + placement pathway | MoU review | Referral MoU | Target | Faisal | Request intro meeting

## Employers
Employer Pipeline & Roles
Employer | Segment | Contact | Role requested | Status | Shortlist sent? | Placement? | Fee | Owner | Notes

## Verification Ops
Verification Throughput & QA
Week | New regs | Tier 1 processed | Tier 1 approved | Tier 2 processed | Tier 2 approved | Backlog | Audit sample | Audit pass % | Notes

## Budget Control
Budget Control — Year 1 (Manual actuals)
Instruction: enter ACTUAL spend monthly; plan figures can be referenced from Annex D.
Month | Planned (USD) | Actual (USD) | Variance | Notes
Month 1
Month 2
Month 3
Month 4
Month 5
Month 6
Month 7
Month 8
Month 9
Month 10
Month 11
Month 12

## Equity & Vesting
Equity & Vesting — Locked Units + Vesting Tracker
As-of date | 2026-02-03
Locked allocations
Holder | Units % | Vesting rule | Start date | Cliff date | Vested % (auto) | Vested Units % | Notes
Greenists (entity) | 0.35 | No vesting (entity) | 2026-02-03 | 2026-02-03 | 1
Maher Farea | 0.25 | 4y vest, 1y cliff | 2026-02-03 | 2027-02-03
Mohammed Faisal Sa | 0.18 | 4y vest, 1y cliff | 2026-02-03 | 2027-02-03
Abdulkawi Al Odaini | 0.12 | Issued pro-rata to cash received | 2026-02-03 | 2026-02-03 | (manual via Contributions) | (manual)
Mohammed Alhakimi | 0.07 | 4y vest, 1y cliff | 2026-02-03 | 2027-02-03
ESOP pool | 0.03 | Vesting grants | 2026-02-03 | 2026-02-03 | 1

## Contributions
Contributions Log — Cash / Time / In-kind (Evidence required)
Date | Contributor | Type | Quantity | Unit | USD value | Proof link/receipt | Notes

## Risks
Risk Register
Risk | Likelihood | Impact | Owner | Mitigation | Status | Next review
Fraud/impersonation | Medium | High | Ops/Verification | Tier1 liveness + audits + duplicates | Open | Monthly
Employer distrust | Medium | High | Maher | Pilot shortlists + SLAs + evidence packs | Open | Monthly
Women drop-out | Medium | High | Faisal | Women-first onboarding + privacy + safe participation | Open | Monthly
Funding shortfall | Medium | High | Abdulkawi | Seed cash + sponsor packages + donor pipeline | Open | Monthly
Payment rails for remote clients | High | Medium | Maher | Start local; add aggregation later | Watching | Quarterly
Data breach | Low | High | Tech Dev | Role-based access + retention + incident response | Open | Monthly

## Decisions
Decision Log (required)
Date | Decision | Why | Who decided | Impact | Follow-up owner | Due date | Status

## Change Log
Change Log (who edited what)
Date | Name | File/Tab | Change summary | Reason | Approved by